## Sheet1
JOINT WMO-IOC STRATEGY FOR DATA MANAGEMENT (2018-2021) - IMPLEMENTATION PLAN
| Outcome | Goals and Objective | Activities | Sub Activities | Deliverables | Lead Responsibility | Other groups Involved | Start (YY/MM) | End (YY/MM) | Priority (1-5) | Aditional Resources | Risks | Comments
1 | Promoting data sharing | Promoting oceanographic and marine meteorological data sharing with the research and operational communities and the private sector in compliance with WMO Resolution 405 (Cg-12), WMO Resolution 606 (Cg-17), and the IOC Oceanographic Data Exchange Policy. | Activity 1 – Plan for the promotion of data sharing and exchange | Produce annual JCOMM report card (JCOMMOPS) | List of relevant events; Communication materials; web site pages (JCOMM, IOC, IODE, WMO); Publications; Annual JCOMM Report card prepared by JCOMMOPS | OCG | collaboration from panels/networks and JCOMMOPS | 10/2018 |  | 2 | funding for events, printing facilities, publication fees; engagement with private sector | Insufficient engagement with the comnmunity will reduce awares of global ocean and climate issues
|  |  | Activity 2 – Plan for enhancing collaboration with the private sector | JCOMMOPS involvment for deployment of platforms from private vessels | List of relevant events; Communication materials; Publications; List of participating private vessels | OCG | with assistance from JCOMMOPS | 01/2019 |  | 2 |  | Not engaging private vessells could potentially reduce the number of platforms that are able to be deployed
2 | Data collection | Achieving more comprehensive, consistent and standardized collection of oceanographic and marine meteorological data from observing platforms in real time and near real time as needed. | Activity 1 - Rationalization and standardization of data collection (collecting of the data) | Evolving and Sustaining Ocean Best Practices Workshop II; Conduct best practices webinars in assocation with IODE | Data collecting;Identifying S&BP needed; Publishing S&BP; | OCG | with assistance from JCOMMOPS, OBP-S | 10/2018 |  | 1 | engagement with private sector | Not engaging community in standards and best practices may result in not-well understood data collections.
|  |  | Activity 2 - Uniformization and standardization of quality control procedures (of the data) |  | Data QC procedures;Identifying S&BP needed; Publishing S&BP; | DMCG | with assistance from OCG, SCG, IODE, OBP-S | 10/2018 |  | 1
3 | Data integration, access, rescue and preservation | Integration of oceanographic and marine meteorological data, their quality control and value adding, including structured and regulated data flow, data rescue, archival/preservation and enhanced data access for end users via WMO and IOC information systems. | Activity 1 – Guidance to Members and Member States on how to use existing oceanographic and marine meteorological and other relevant data systems, including description of governance and processes |  | S&BP on use of data; tutorials on use of data; | DMCG | with assistance from OCG and IODE | 11/2018 |  | 2
|  |  | Activity 2 – Marine Climate Data System (MCDS) / Development of the CMOC Network in collaboration with IODE | IPET-MOIS to coordinate with ETMC and ETDMP | CMOCs established; Metrics for MCDS on CMOCs; | DMCG and IPET-MOIS | with assistance from OCG, IODE, ETMC and ETDMP | 10/2018 |  | 1
|  |  | Activity 3 – Marine Climate Data System (MCDS) / Development of the DAC and GDAC Network in collaboration with IODE | ETMC to produce the list of potential candidates with involvement of IODE, ETDMP and IPET-MOIS | GDACs, DACs established; Metrics for MCDS on GDACs, DACs | DMCG and ETMC | with assistance from OCG, IODE, Expert Team on Data Management practices (ETDMP) and IPET-MOIS | 10/2018 |  | 1
|  |  | Activity 4 – Accessibility of oceanographic and marine meteorological data by the ocean community to GTS data in near real-time | Continue submitting Saildrone mission MET data to GTS; Develop new Unmanned Surface Vehicle (USV) BUFR template with TT-TDC; Develop Open Access to GTS strategy document. Develop data metadata interchange methodologies between ODIS and WIS. | Data available via OpenGTS; USV BUFR template; OpenGTS stragety documents; Identfication of marne datacetners to publish data to the WIS | OCG, IPET-MOIS | with the support from members and members states and WMO/WIGOS | 10/2018 |  | 1 | support for project is needed; Identification of data centers willing to partcipate (IMOS, BODC, Irish Marine Insitute) is necessary to expand project. Support for IPET-MOIS to meet with collaborate with oceanographic data cetners/aggregators towards meeting the objective of grater data interchange between ODIS and WIS. | Ocean data not making it to the GTS is not being used to its fullest potential; Data sent to the GTS in an ad-hoc template may result in that data not being used by forecast centers; It is imperative that a well-developed strategy is formed for opening access to the GTS to ensure that the data on GTS meets the expected quality standards
|  |  | Activity 5 – Integration of oceanographic and marine meteorological observations by variable-based products, including value-added and bias correction |  | EOV/ECV-based products available online; updated products from MCDS CMOCs; | DMCG | with assistance from OCG, SCG, AtlantOS | 10/2018
|  |  | Activity 6 - Scientific Stewardship |  | Catalogue of centres documenting QA/QC; Documentation of QA/QC | GOOS | DMCG, SCG, DMCG, IODE | 10/2018 |  | 3
|  |  | Activity 7 – Data Rescue |  | S&BP on data rescue; Guidance on crowdsourcing data rescue activities; MCDS CMOCs data sets; | DMCG | ETMC with the assistance from IODE and Global Oceanographic Data Archaeology and Rescue (GODAR) | 10/2018 |  | 2 | sustainable project for data rescue is needed
|  |  | Activity 8 – Integrated access to oceanographic and marine meteorological data and products using modern technology | Continue work with OCG networks to integrated delated mode data offerings through ERDDAP services | Data and products available via web services; | OCG | DMCG, SCG | 10/2018 |  | 3 | Some support may be needed to encourage DACs and GDACs to improve data management workflows and data and metadata accessibility | Proliferation of non-uniform and non-standard access services will decrease the interoperability and therefore usefulness of the data | Improved access to data via interoperable systems is criticial for the development of EOVs
4 | Data Dissemination | Achieving more comprehensive, consistent and standardized distribution of oceanographic and marine meteorological data to end users in real time and near real time as needed. | Activity 1 – Modernized and new data management practices and standards |  | S&BP on data management; | DMCG | collaboratively led by DMCG, IODE, Expert Team on Data Management practices (ETDMP) and JCOMM Expert Team on oceanographic and marine meteorological Data Forecasting Systems for WIS(IPET-MOIS), also with the assistance form Ocean Data Standards(ODS) within IODE | 10/2018 |  | 1
|  |  | Activity 2 – New and updated templates for Table Driven Codes |  | templates for TDC; S&BP on TDC; | DMCG | TDC, OCG as needed | 10/2018 |  | 2
5 | Data discovery | Making oceanographic and marine meteorological data sets discoverable using WMO and IOC information systems. | Activity 1 – Interoperability of oceanographic and marine meteorological data sets and products with the WMO Information System (WIS) |  | WIS-compiant metadata (WMO Core Profile);WIS-comliant services;Data and products available for WIS; | DMCG | OGC, SCG | 10/2018 |  | 2 | support for related ODIS services (such projects as IODE ODP, OBIS, WOD, GOSUD, GTSPP, IQUOD, etc.)is needed
|  |  | Activity 2 – Interoperability of oceanographic and marine meteorological data sets and products with the Ocean Data Information System (ODIS) including ODP ( MCDS, WIS, ….) | ETDMP to inform the IPET-MOIS on achievements and activities with regards to ODIS | List of data sources; Metadata catalogues; Data repositories; Services; | DMCG and ETDMP | OGC, SCG, Expert Team on Data Management practices (ETDMP) and IPET-MOIS | 03/2019 |  | 2 |  |  | connected to Act.1; OCG should work with MCDS to ensure platform-based delayed mode data is integrated into MCDS
|  |  | Activity 3 - Evaluate new evolving technologies such as Big Data (BG) , Cloud Computing (CC) for metadata discoverability to adopt in JCOMM DM |  | Overview of the evolving technologies for metadata discoverability; Requirements to discovery metadata; | DMCG | consultation is needed | 12/2019 |  | 5 | consultation from private sector (IT) is needed
6 | Capacity Development | Enhanced capacities of Members/Member States with regard to oceanographic and marine meteorological data management. | Activity 1 – Capacity development and training on oceanographic and marine meteorological data management |  | Training progremmes; training materials | JCOMM MAN | with collaboration from IODE OTGA, coordinators for JCOMM CD | 10/2018 |  | 3