North Pacific data buoy advisory panel (NPDBAP) Report

Thirty-SIXth session of the DBCP (DBCP-36)

(Virtual session, 05-08 Oct 2020)

1) Summary

| Name of Action Group | DBCP-PICES North Pacific Data Buoy Advisory Panel (NPDBAP) |
| --- | --- |
| Date of report | 16 September 2020 |
| Overview and main requirements addressed | The goals of the NPDBAP are to deploy 60 SVPB drifters a year, and maintain 75 active buoys in the region. |
| Area of interest | North Pacific Ocean and marginal seas generally north of 30°N |
| Type of platform and variables measured | Lagrangian drifters measuring sea level pressure, SST, and sea-surface velocity |
| Targeted horizontal resolution | 5° x 5° |
| Chairperson/Managers | Co-Chairperson for the NE Pacific: Ms. Laura Medeiros, Environment Canada, Canada Co-Chairperson for the NW Pacific: Dr. BG Lee, Jeju National University, South Korea |
| Coordinator | Mr Shaun Dolk, NOAA / AOML |
| Participants | Laura Mederios, Rick Lumpkin, BG Lee, Shaun Dolk, Ignatius Rigor, Long Jiang, Mayra Pazos, Jooyoung Lee, Mathieu Ouellet, Serge Hagan-Deschamps, Myungwon Park, Sang Kill Park |
| Data centre(s) | Drifter Data Assembly Centre (DAC) Integrated Science Data Management (ISDM), Canada |
| Website | http://dbcp.jcommops.org/npdbap/ |
| Meetings | Yearly meetings usually held in conjunction with DBCP meetings. Next meeting planned 05 October 2020 as a virtual session. |
| Current status summary | From 01 September 2019 to 31 August 2020, 63 drifters were deployed in the North Pacific Ocean. Of the 63 drifter deployments, 35 units were equipped with barometer sensors (three of which also captured wave measurments!) and the remaining 28 drifters were standard SVP type drifters. |
| Summary of plans for 2021 | The goal for 2021 is to deploy 75 drifters, of which, 50 drifters will be equipped with barometer sensors. |

2	Deployment plans for 2021

Both the GDP and Environment Canada will continue to utilize ships of opportunity for drifter deployments, while also looking for new possibilities within the Canadian and United States Coast Guards..

3	Data management

3.1	Distribution of the data

The drifter Data Assembly Center (DAC) assembles, quality controls, and interpolates data from approximately 1500 drifters per month from all GDP national and international partners, throughout the world’s oceans.  These data are made available through the web (http://www.aoml.noaa.gov/phod/gdp/interpolated/data/all.php) in delayed (~ 2 months) mode. At the time this report was generated (September 2020), quality controlled data are available through March 2020.

3.1.1	Data policy

The DAC, located at NOAA’s Atlantic Oceanographic and Meteorological Laboratory (AOML) has access to drifters from GDP partners that have given Service Argos and Iridium VARs permission to make these data available to the DAC.  In return, the partners have access to all quality controlled and interpolated data available in the database via the World Wide Web.  Non-interpolated quality controlled data and raw data are made available via ftp transfer upon request.

3.1.2	Real-time data exchange

All data from drifters in the GDP’s programs are disseminated via GTS at the time of deployment.  The GDP monitors data going onto the GTS, and transmissions of sensors producing bad data, or transmissions from grounded drifters, are removed from the GTS data stream.

The GDP does not monitor GTS data timeliness and relies on operational centres to report on these issues.

3.1.3	Delayed mode data exchange

Drifter data (raw Argos data, edited non-interpolated and interpolated data) are archived at AOML.  These datasets are also sent once or twice a year with a 6-month delay to Integrated Science Data Management (ISDM), the RNODC for drifter data, for permanent archival and further distribution.

Metadata for GDP drifters are received directly from drifter manufacturers.  Portions of this metadata are extracted and are made available on the deployment log at the GDP web page (http://www.aoml.noaa.gov/phod/dac/deployed.html).  Specification sheets are archived at AOML.

Deployment date, date of last transmission, drogue off and cause of death metadata are determined during quality control of the dataset and are made available through the web at http://www.aoml.noaa.gov/phod/dac/dirall.html.  These web pages are ingested by JCOMMOPS to gather information for their metadata systems.

3.2	Data quality

4) Instrument practices

5) Other issues as needed

__________________

Annex (optional)

Status maps and graphics