Financial Report

GOOS Observations Coordination Group

Brest, France

May 2021

M. Belbéoch and E. Rusciano

Special thanks to A. Fischer, E. Heslop and C. Gallage for inputs and review, and for the continuous secretarial support provided.

www.ocean-ops.org

Joint WMO-IOC Centre for Oceanography and Marine Meteorology
 in-situ Observations Programme Support

Index

INTRODUCTION	3

CONTRIBUTIONS 2020	4

NETWORKS and PROJECTS CONTRIBUTIONS 2020	5

CONSOLIDATED OceanOPS ACCOUNTING 2020	6

INTERIM BUDGET 2021	9

ANTICIPATED BUDGET 2022	12

CONCLUSIONS and RECOMMENDATIONS	14

OFFICIAL STATEMENTS	17

# INTRODUCTION

This document provides the yearly OceanOPS financial report for calendar year 2020, the interim budget for 2021 and the anticipated budget for 2022.

The interim and anticipated budgets will be validated by OCG during the upcoming OCG-12 meeting in May 2021.

All official statements account and budget information can be requested to Emanuela Rusciano erusciano@ocean-ops.org

Disclaimer

The information provided in this report could be affected by a small percentage of error due to the different currency rate exchanges in the different Trust Funds.

# CONTRIBUTIONS 2020

During 2020, about 900k$ were received vs 1M$ in 2019, and 569K$ in 2018.

The total 900k$ contributions includes funds from regular national contributions, and also European Projects in which OceanOPS is involved and delivering numerous deliverables in line with its 5-year strategy.

Main highlights for 2020 contributions:

- Regular national contributions from networks are stable, diversified and lightly strengthened around 680 k$ per year.

- European Projects (EuroSea, EuroArgo-RISE, TRUSTED and Seadatanet) still participate in the budget increase at the level of 120 k$ per year.

- 17k$ were received from IOC/UNESCO budget (GOOS).

- Monaco provided 83k$ to enable the Argo BGC expansion and support the new regional node for the Mediterranean Sea.

- As requested at OCG-11, IOC cash flow is now rigorously monitored through a dedicated spreadsheet - important to track closely for ‘continuous’ short-term staff contracts - an issue that OceanOPS will seek to resolve in 2022 (see later).

- Eumetnet/ESURFMAR contribution has slightly increased.

Note: The 31 EUMETNET members' contribution is now clearly identified, representing 4.75% or 43k$. European Union contribution comes from Euro-Argo European Research Infrastructure Consortium representing 0.67% or 6k$.

The international diversity of funding sources is important for the centre, but it is not achieved for all networks and action is needed to broaden and diversify funding base for some networks (see next section).

# NETWORKS and PROJECTS CONTRIBUTIONS 2020

Note: contributions tagged OceanOPS are provided by USA, France, Monaco and European Projects for an integrated support to OCG networks.

OceanGliders, OceanSITES and GO-SHIP benefit from dedicated OceanOPS staff, as well as common infrastructure staff (lead, IT, metadata, communication) and outsourced developments, and are encouraged to increase their contributions to help OceanOPS to sustain this support:

- OceanGliders support is only coming from USA and European projects (38k$).

- OceanSITES support comes from USA, France and European projects (41k$).

- GO-SHIP support comes from USA, Australia and European projects (39 k$).

However, the Eurosea project has been used as a mechanism from these Networks to fund these activities adding about 23k$ per year to each of these amounts (cashed only in 2019 and 2021 due to WMO administrative regulations) if we smooth them over 3 years.

More information on the OceanOPS 2020 activities for such networks are available in the workplan report to OCG.

Recommendations for Networks are introduced in the conclusion of the report.

European Projects contribute to OceanOPS at the level of 123 k$, including:

- TRUSTED 3k$ (Copernicus, HRSST drifters) - last year

- SeaDataCloud 40k$ (metadata harmonization) - last year

- EuroSea 39k$ (OCG Networks and regional observing systems)

- EuroARGO-RISE 41k$ (Argo) - last year

The Argo program is the first Network contribution into OceanOPS sustaining a third of its resources. Another third comes through an integrated OceanOPS support, and the remaining third comes from all other networks.

# CONSOLIDATED OceanOPS ACCOUNTING 2020

Main features:

- OceanOPS operated in 2020 with 1.2 M$ available budget and spent 897 k$.

- Yearly balance is positive, and carry forward is reasonable (320k$) and includes a cash flow build up for new staff (Argo BGC/Med. Sea coordinator), and European projects deferred funds to 2021 to support core staff and sustain the Metadata consultant.

- National contributions were slightly increased but a few were not possible (administrative issues due to COVID).

- Project contributions show a light decrease as some projects were ending, but are still substantial (from 174k$ to 123k$).

- All projects are now monitored individually for better reporting and to ensure a spending plan (mainly on staff) according deliverables.

2020 Budget:

| Item / USD $ | JCOMM TF | WMO/WHOI TF | DBCP TF | IOC TF | CLS TF | 2020 BUDGET |
| --- | --- | --- | --- | --- | --- | --- |
| INCOMES |  |  |  |  |  |  |
| CARRY FORWARD AT 2020-01-01 | 47,442 |  | 187,633 | 77,714 | 2,378 | 315,167 |
| CONTRIBUTIONS |  | 475,195 | 87,492 | 93,455 | 22,517 | 678,659 |
| TRUSTED |  |  |  |  | 3,163 | 3,163 |
| EUROARGO-RISE project 2/2 |  |  | 41,012 |  |  | 41,012 |
| IOC co-investment |  |  |  | 17,120 |  | 17,120 |
| EUROSEA (IOC) 2/3 |  |  |  | 39,000 |  | 39,000 |
| Seadatacloud EU Project - END |  |  | 40,000 |  |  | 40,000 |
| Monaco |  |  |  | 82,938 |  | 82,938 |
| EMODNET |  |  |  | 0 |  |  |
| TOTAL AVAILABLE BUDGET 2020 | 47,442 | 475,195 | 356,137 | 310,227 | 28,058 | 1,217,059 |
| EXPENSES |  |  |  |  |  |  |
| TC Argo / JCOMMOPS Lead position |  | 133,000 | 6,883 |  |  | 139,883 |
| TC DBCP / OceanSITES position |  | 129,864 |  |  |  | 129,864 |
| TC SOT/GO-SHIP/Cruises position | 44,338 | 79,280 |  |  |  | 123,618 |
| I.T. Engineer position (CLS) |  | 50,863 |  |  |  | 50,863 |
| TC Science Communication position |  |  |  | 60,435 |  | 60,435 |
| TC Gliders / Regional (12 months) |  |  |  | 96,000 |  | 96,000 |
| TOTAL STAFF | 44,338 | 393,007 | 6,883 | 156,435 | 0 | 600,663 |
| TC Argo/JCOMMOPS travels |  |  | 1,595 | 1,548 |  | 3,143 |
| TC DBCP/OceanSITES travels |  |  | (318) |  |  | (318) |
| TC SOT/GO-SHIP travels |  |  |  |  | 326 | 326 |
| I.T. Engineer travels |  |  |  |  |  | 0 |
| TC Science Communication travels |  |  | 3,170 |  |  | 3,170 |
| TC Gliders / Regional |  |  |  |  |  | 0 |
| TOTAL MISSION | 0 |  | 4,447 | 1,548 | 326 | 6,321 |
| I.T. Hosting (CLS) |  |  | 55,730 |  |  | 55,730 |
| Activities (meetings, supplies, misc.) rebrand + stickers logo |  |  |  |  | 1,529 | 1,529 |
| TOTAL INFRASTRUCTURE | 0 | 0 | 55,730 | 0 | 1,529 | 57,259 |
| OVERHEAD | 3,104 | 27,510 | 6,906 | 11,059 |  | 48,579 |
| TOTAL OPERATIONAL BUDGET (EXPENSES) | 47,442 | 420,517 | 73,966 | 169,042 | 1,855 | 712,822 |
| STAFF SALARY 100% RESERVE | 44,338 | 393,007 |  | 156,435 |  | 593,780 |
| BUDGET AVAILABLE FOR PROJECTS |  |  | 282,171 | (15,251) | 26,204 | (89,543) |
| Project #1: Communication (Report Card) |  |  |  |  | 10,401 | 10,401 |
| Project #2: Communication (Strategy) |  |  |  |  | 6,677 | 6,677 |
| Project #3: Web Development Support (10 months) |  |  | 95,851 |  | 3,938 | 99,789 |
| Project #4: Metadata Support - consultant (11 months) |  |  | 67,297 |  |  | 67,297 |
| TOTAL DEVELOPMENTS / PROJECTS | 0 |  | 163,148 | 0 | 21,016 | 184,164 |
| TOTAL EXPENSES | 47,442 | 420,517 | 237,114 | 169,042 | 22,871 | 896,986 |
| BALANCE 2020-12-31 | 0 | 54,678 | 119,023 | 141,184 | 5,187 | 320,073 |

2020 Expenditures:

| 2020 Expenditures | $ |
| --- | --- |
| Staff | 600,663 |
| Mission | 6,321 |
| Infrastructure | 57,259 |
| IT Development | 99,789 |
| Metadata Support | 67,297 |
| Communication | 17,078 |
| Financial Charges | 48,579 |
| Total | 896,986 |

Main highlights for 2020 expenditures:

- 2020 was an ideal year in terms of resources enabling OceanOPS to operate at full speed. This was allowed through our carry forward from 2019 (mainly from European projects) and spent on Metadata consultant support (11 months) and outsourced web developments (4 months).

- Mission budget was dramatically decreased due to the international travelling restrictions, with only a few missions performed just before the first lock down period (March 2020).

- A consultant was hired to support the work on metadata challenges across several networks, with great achievements on moored buoys, ships, and cruises metadata.

- Outsourced Web developments to improve our web dashboard for all Networks (in particular OceanGliders and OceanSITES) were fully carried out through 11 months of contracting.

- All staff members have been operating full time (vs 2019 where Oceangliders staff recruited mid year worked 7 months only).

- Communication expenses were slightly increased to absorb the rebranding and strategy publication needs.

- Operational costs to support the infrastructure (IT) are very reasonable for such an operational centre, and as high as the financial charges and overheads. As we will open a call for proposals to host the IT infrastructure late 2021, we will compare costs amongst bidders. It could also be interesting to investigate such costs for similar operational centres.

Balance:

2020 yearly contributions + carried over (1,217M$) – 2020 Expenditures (897 K$) = 320 K$.

Carried over at 01 January 2021 is 320 K$ including carry forward from national contributions and projects.

In summary for 2020OceanOPS has managed its operational budget carefully and expanded its activities slightly thanks to European projects.
The carry forward (in particular at IOC) includes a reserve to enable the new part time position to support BGC Argo and the Mediterranean OceanOPS node (83 k$).

Other carry forward at WMO are EU projects funding to be spent in 2021 (120 k$).

Remaining carry forward (117k$) is a small cash flow reserve needed to renew contracts in time.

The contributions are received all along the year from about 20 sources, and the resultant fluctuating cash flow (in particular at IOC) places a huge pressure on contracts renewal, management team (IOC secretariat and OceanOPS) and staff.

The setup of a new staff to support OceanGliders is not generating further commitments despite the excellent support provided by the incumbent, and has resulted in some drain on core resources and impacted contract length for other staff. This forces OceanOPS to be much more careful for future expansions (e.g. Argo BGC/Regional) and reserve some overhead (for example 20 - 30%, to be discussed by OCG) for OceanOPS central activities rather than using core funds to absorb the lack of commitments or delayed contributions.

It should be noted as well the considerable administrative efforts that are required by OceanOPS and both secretariats to enable these new positions.

All the challenges to manage the budget through the different Trust Funds at IOC and WMO, have in general been resolved, and OceanOPS, IOC and WMO secretariat now have regular quarterly meetings and the proper tools to oversee the consolidated budget and plan expenses properly.

# INTERIM BUDGET 2021

2021 anticipated budget will be at the same level of 2020 with still a strong financial support from  European projects (184 k$).

Main highlights:

- National contributions are expected to be stable, except for the USA planning a ~10% budget cut, which translates overall to a budget cut of 5% (since the US is contributing 50% of OceanOPS budget, as of 2020).

- China is joining Monaco in supporting the BGC Argo/regional position establishment (15 k$).

- WMO has been contributing to the budget through a one-off contribution of 49 k$ enabled by unspent funds in the secretariat and generously channeled to OceanOPS.

- WMO is presently recruiting an OceanOPS manager position through its regular budget which is a major contribution to OceanOPS raising its overall budget by 15%. This should happen by October 2021 but this interim budget does not consider yet the potential savings this will generate. WMO strongly replied to the OceanOPS 5-year strategic plan call for action.

- The 2022 anticipated budget will clarify how this increase will impact OceanOPS, mainly through the stabilization of core staff (see next section).

- The Metadata consultant should be hired through a more stable contract via WMO at mid year, to continue this vital work.

- A new coordinator to support Argo BGC expansion and integrated regional observations in the Mediterranean Sea  should be hired, ⅗ FTE by mid year.

- Travel budget is set to the strict minimum, and is likely to be underspent, enabling probably a couple of travels very late in the year,  if restrictions allow.

- Anticipated Web developments will be slightly decreased but still comfortable (9 months) and this year we will use this resource to develop a more interactive web version of the report card and include it in the main dashboard and work on the regional dashboard (EuroSea project).

2021 Budget:

| Item / USD $ | WMO/WHOI TF | DBCP TF | IOC TF | CLS TF | 2021 BUDGET |
| --- | --- | --- | --- | --- | --- |
| INCOMES |  |  |  |  |  |
| CARRY FORWARD AT 2021-01-01 | 54,678 | 500 | 141,184 | 5,187 | 201,550 |
| CARRY FORWARD PROJECTS |  | 118,522 |  |  | 118,522 |
| EXPECTED CONTRIBUTIONS | 413,428 | 87,492 | 85,000 | 37,724 | 623,644 |
| WMO contribution |  | 49,836 |  |  | 49,836 |
| Monaco |  |  | 82,938 |  | 82,938 |
| EMODNET |  |  | 64,900 |  | 64,900 |
| EUROSEA (WMO) 3/3 |  | 159,160 |  |  | 159,160 |
| EUROSEA (IOC) 3/3 |  |  | 25,000 |  | 25,000 |
| TOTAL AVAILABLE BUDGET 2020 | 468,106 | 415,510 | 399,022 | 42,911 | 1,325,550 |
| EXPENSES |  |  |  |  |  |
| TC Argo / JCOMMOPS Lead position | 120,000 | 30,000 |  |  | 150,000 |
| TC DBCP / OceanSITES position | 79,000 | 51,000 |  |  | 130,000 |
| TC SOT/GO-SHIP/Cruises position | 92,000 | 33,000 |  |  | 125,000 |
| I.T. Engineer position - CLS | 81,000 |  |  |  | 81,000 |
| Metadata/DB assistant - G4 6/12 |  | 32,500 |  |  | 32,500 |
| TC Science Communication position |  |  | 60,000 |  | 60,000 |
| TC Gliders / Regional (12 months) |  |  | 96,000 |  | 96,000 |
| TC BGC Argo / Med. Sea (6 months) |  |  | 48,000 |  | 48,000 |
| TOTAL STAFF | 372,000 | 146,500 | 204,000 | 0 | 722,500 |
| TC Argo/JCOMMOPS travels |  | 2,000 |  |  | 2,000 |
| TC DBCP/OceanSITES travels |  | 2,000 |  |  | 2,000 |
| TC SOT/GO-SHIP travels |  | 2,000 |  |  | 2,000 |
| I.T. Engineer travels |  | 2,000 |  |  | 2,000 |
| Metadata/DB assistant - G4 |  | 0 |  |  | 0 |
| TC Science Communication travels |  | 2,000 |  |  | 2,000 |
| TC Gliders / Regional |  | 2,000 |  |  | 2,000 |
| TC BGC Argo / Med. Sea (6 months) |  | 0 |  |  | 0 |
| TOTAL MISSION | 0 | 12,000 | 0 | 0 | 12,000 |
| I.T. Hosting (CLS) |  | 53,500 |  |  | 53,500 |
| Activities (meetings, supplies, misc.) |  |  |  | 715 | 715 |
| TOTAL INFRASTRUCTURE | 0 | 53,500 | 0 | 715 | 54,215 |
| OVERHEAD | 26,040 | 6,360 | 14,280 | 0 | 46,680 |
| TOTAL OPERATIONAL BUDGET (EXPENSES) | 398,040 | 218,360 | 218,280 | 715 | 835,395 |
| STAFF SALARY 100% RESERVE | 372,000 | 32,500 | 156,000 | 0 | 560,500 |
| BUDGET AVAILABLE FOR PROJECTS | 0 | 197,150 | 24,742 | 42,196 | (70,345) |
| Project #1: Communication (Report Card) |  |  |  | 13,200 | 13,200 |
| Project #2: Web Development Support 8+1 months |  | 64,000 |  | 8,800 | 72,800 |
| TOTAL DEVELOPMENTS / PROJECTS | 0 | 64,000 | 0 | 22,000 | 86,000 |
| TOTAL EXPENSES | 398,040 | 282,360 | 218,280 | 22,715 | 921,395 |
| BALANCE 2020-12-31 | 70,066 | 133,150 | 180,742 | 20,196 | 404,155 |

latest update 12/05/2021

2021 Expenditures:

| 2021 Expenditures | $ |
| --- | --- |
| Staff | 722,500 |
| Mission | 12,000 |
| Infrastructure | 54,215 |
| IT Development | 72,800 |
| Communication | 13,200 |
| Financial Charges | 46,680 |
| Total | 921,395 |

# ANTICIPATED BUDGET 2022

The year 2022 will mark an important step forward in the stabilization of the core OceanOPS staff, in line with the 5-year strategic plan.

The continuous cash flow challenges (at IOC) need to be addressed towards a stable situation. 
The substantial WMO contribution would enable a number of improvements, and staff changes, to be approved by the OCG 12 session:

- OceanOPS will have a dedicated manager (see position description ) funded by WMO, and overall budget will increase by 15%.

- Current OceanGliders/Regional position at IOC will be ended (the 2-year contract had to be renewed anyway and we do not have necessary cash flow to sustain it).

- The Argo Coordinator function at WMO will be fusioned with OceanGliders support and generalized to a “mobile subsurface systems focal point” (including as well AniBOS as far as funding allows).

- An IT manager position will be open at WMO, transitioning the contract with CLS accordingly. The securing and upgrade of this function is seen as the highest priority for OceanOPS sustainability and risk reduction.

The substantial US contribution at WMO, completed by other regular contributions, and transfer of required funds from IOC to WMO (~25k$) allows this transition with some margin.

470 k$ (overheads included) are needed to sustain the 4 WMO core staff (US contributing 413 k$ per year, and other countries contributing 113k$).

This arrangement should ensure greater contract stability for the 6 OceanOPS core staff,both at IOC and WMO. The core staff roles will be as follows:

- Manager (WMO)

- Subsurface platforms focal point (WMO)

- Surface/fixed platforms focal point (WMO)

- Ship based platforms focal point (WMO)

- IT manager (WMO)

- Communication manager (IOC)

Highlights on 2022 budget:

- National contributions are expected to be stable.

- carry forward from Eurosea/WMO and EuroArgo-RISE projects (114k$) will be spent for the Metadata Consultant and also on core staff (as contracted), which will participate in building up cash flow for core staff.

- Contribution from Monaco (initial 2 year commitment) is expected to continue, and to be complemented by other countries, provided the position is successfully meeting expectations. If not, the position will be closed. If funds allow, the position will be extended to a full time role.

- It is not certain that the EMODNet contribution will continue.

- Overall staff cost will decrease! Mechanical effect of the WMO support (~150k$ savings) allows it to stop the OceanGliders position at IOC and transfer it to WMO.

- Travel budget will be minimalist anticipating the post-covid era travel sobriety and maximizing of virtual opportunities.

- Anticipated web developments are for now minimized and might be increased if cash flow allows.

2022 Expenditures plan:

| 2022 Expenditures | $ |
| --- | --- |
| Staff | 640,000 |
| Mission | 22,500 |
| Infrastructure | 53,500 |
| IT Development | 32,000 |
| Communication | 15,000 |
| Financial Charges | 40,920 |
| Total | 803,920 |

Anticipated 2022 budget:

| Item / USD $ | WMO/WHOI TF | DBCP TF | IOC TF | CLS TF | 2022 BUDGET |
| --- | --- | --- | --- | --- | --- |
| INCOMES |  |  |  |  |  |
| CARRY FORWARD AT 2021-01-01 | 70,066 | 20,328 | 180,742 | 20,196 | 291,332 |
| EXPECTED CONTRIBUTIONS | 413,428 | 112,492 | 60,000 | 22,724 | 608,644 |
| Monaco |  |  | 82,938 |  | 82,938 |
| EMODNET |  |  | 64,900 |  | 64,900 |
| Carry forward - EuroSea Project |  | 106,805 |  |  |  |
| Carry forward - EuroArgo-RISE Project |  | 7,623 |  |  |  |
| TOTAL AVAILABLE BUDGET 2020 | 483,494 | 247,247 | 388,580 | 42,920 | 1,162,242 |
| EXPENSES |  |  |  |  |  |
| OceanOPS Lead | 0 |  |  |  | 0 |
| TC Argo / OceanGliders position | 99,000 | 11,000 |  |  | 110,000 |
| TC DBCP / OceanSITES position | 93,000 | 17,000 |  |  | 110,000 |
| TC SOT/GO-SHIP/Cruises position | 114,000 | 11,000 |  |  | 125,000 |
| I.T. Engineer position | 55,000 | 55,000 |  |  | 110,000 |
| TC Science Communication position |  |  | 60,000 |  | 60,000 |
| Metadata/DB assistant - G4 (12 months) |  | 65,000 |  |  | 65,000 |
| TC BGC Argo / Med. Sea (12 months ⅗ FTE) |  |  | 60,000 |  | 60,000 |
| TOTAL STAFF | 361,000 | 159,000 | 120,000 | 0 | 640,000 |
| TC Argo/OceanGliders travels |  | 5,000 |  |  | 5,000 |
| TC DBCP/OceanSITES travels |  | 5,000 |  |  | 5,000 |
| TC SOT/GO-SHIP travels |  | 5,000 |  |  | 5,000 |
| I.T. Engineer travels |  | 2,500 |  |  | 2,500 |
| Metadata/DB assistant - G4 |  | 0 |  |  | 0 |
| TC Science Communication travels |  |  | 2,500 |  | 2,500 |
| TC BGC Argo / Med. Sea (6 months) |  |  | 2,500 |  | 2,500 |
| TOTAL MISSION | 0 | 17,500 | 5,000 |  | 22,500 |
| I.T. Hosting (Cloud) |  | 53,500 |  |  | 53,500 |
| Activities (meetings, supplies, misc.) |  |  |  |  | 0 |
| TOTAL INFRASTRUCTURE | 0 | 53,500 | 0 |  | 53,500 |
| OVERHEAD | 25,270 | 6,900 | 8,750 |  | 40,920 |
| TOTAL OPERATIONAL BUDGET (EXPENSES) | 386,270 | 236,900 | 133,750 |  | 756,920 |
| Project #1: Communication (Report Card) |  |  |  | 15,000 | 15,000 |
| Project #2: Web Development 1+3 months |  | 8,000 |  | 24,000 | 32,000 |
| TOTAL DEVELOPMENTS / PROJECTS | 0 | 8,000 | 0 | 39,000 | 47,000 |
| TOTAL EXPENSES | 386,270 | 244,900 | 133,750 | 39,000 | 803,920 |
| BALANCE 2020-12-31 | 97,224 | 2,347 | 254,830 | 3,920 | 358,322 |

The 2022 budget (and 2021 if manager position starts earlier) will show the contribution of the WMO in the overall national contribution to OceanOPS, and related expenses on the manager position costs,  and clearly appear in the pie chart of contributors. For now we just put 0 in the cost.

# CONCLUSIONS and RECOMMENDATIONS

As 2019, 2020 was one of the best years for OceanOPS budget which allowed the centre to operate at full speed sustaining the two “new” resources (a new Technical Coordinator for OceanGliders and a metadata expert). This was possible only thanks to the strong contribution from European projects into OceanOPS, and travel budget savings.

From 2021, OceanOPS will strongly support the OneArgo UN Decade Programme/Project towards its multidisciplinary expansion and pilot a new regional function in the Mediterranean region (funded by Monaco and China, and potentially others) that could lead to further opportunities.

In 2022, OceanOPS will start to reduce the sail, mainly on web developments and travels, anticipating the end of the projects’ support.
If nothing is done to improve the budget, the trajectory for 2023 will have even more constraints, which will force us to end our metadata consultant support which is seen essential to meet our strategy goal #2 (Lead metadata standardization and integration), and will halt the great progress made so far.

Under funded networks:

Some Networks have not progressed enough to raise their contributions: OceanGliders, OceanSITES and GO-SHIP have levels of contributions that do not support the work required and achieved. However these Networks have used a European Project as a mechanism to temporarily support the activities, which raised their overall contribution to the level of 60k$/year and which is a positive step forward.

Cost of of the OceanOPS - core and network focused:

1M$ per year: this is what is needed for such a centre to operate properly and deliver its services to the 6 OCG networks that it supports (Argo, DBCP, GO-SHIP, OceanSITES, OceanGliders and SOT) and serve the integrated GOOS perspective.
If we make the hypothesis that support is equally distributed amongst networks, we then expect the funding is as well balanced accordingly (consensus of OCG 9).
In the proposed light restructuring of OceanOPS Technical coordinators role, each of the TC supports today 2 Networks.

50% out of 1M$ is needed to sustain the Network experts (responsible each for 2 Networks) - this is already covered by national contributions but not well balanced amongst networks. Ideally these 500k$ should be splitted equally amongst the 6 networks (i.e. 500k$ / 6 networks = 84k$)

While, remaining 50% (or 500 k$ out of 1M$) is needed to sustain the integrated functions of the centre, including:

- Manager

- IT infrastructure, IT manager, and metadata support

- Communication manager

Currently, 30% out of these 50% (300k$) for OceanOPS integrated functions are already supported by existing integrated and regular contributions (~150 k$ mainly from USA, France) and complemented by the new WMO support (~150k$). Therefore we need to find an additional 20% (200k$) to support integrated functions, which again should be splitted equally amongst the 6 networks (i.e. 200k$ / 6 = 33k$)

Suggestion:

Each network should contribute 84k$ for networks experts + 33k$ for integrated functions = 116k$. Therefore, 116k$*6= 696k$ + 150k$ from USA & France +150 k$ from WMO= 1M$.

Argo and DBCP already contribute more than 116k$ (see stable contribution chart below), while OceanGliders, OceanSITES and SOT should progress to reach the necessary 116k$ per Network.

The chart above clearly highlights the Networks that need to increase their effort, noting 4 of them are at mid way through ad hoc projects funding, and two of them are meeting and even exceeding requirements, which calls for a specific delivery in the anticipated workplan.

Recommendations for more stable funding:

The strategy to reach such level of funding for OceanOPS should be organized around the following:

- GO-SHIP, OceanGliders, OceanSITES and SOT should clearly communicate the suggested budget targets to their Steering Teams.

- OCG should as well report at its 12th session on this challenge and make appropriate recommendations.

- OceanOPS through the promotion of its strategic plan, should seek core funding, in particular in the host country and Europe.

- While WMO has responded strongly to the challenge, we have to work with IOC, GOOS implementation plan and UN decade to progress further. The GOOS Steering Committee has recognized the importance and central role of OceanOPS, representing about 50% of existing human resources in the GOOS core team.

The opportunities offered by European projects had a positive impact on our resources but came with a strong overhead on administrative issues (funding management, reporting). It also orientates OceanOPS workload on the European activities, while its mandate is broader and truly international.
We are hoping that this European temporary focus will be fruitful in terms of funding as OceanOPS role and visibility in Europe have been clearly elevated.

That said, OceanOPS does not believe projects are a long term solution to support its budget and activities.

OceanOPS is confident that if the 4 suggested recommendations above are actively addressed, with tangible results starting in 2022, and progressing gradually along the next years, its 5-year strategic plan will be fully implemented by 2025.

# OFFICIAL STATEMENTS

CLS 2020 Trust Fund

Across the various IOC and WMO managed trust funds and project budget lines