| World Meteorological Organization & Intergovernmental Oceanographic Commission (of UNESCO) GLOBAL OCEAN OBSERVING SYSTEM/OBSERVATIONS COORDINATION GEORP Ship Observations Team Eleventh Session Virtual Session, 13-16 September 2021 | SOT-11/Doc. 9.1.1 |
| --- | --- |
|  | Submitted by: Henry KLETA 27.08.2021 DRAFT 1 |

AGENDA ITEM 9.1.1:	VOS PANEL - Activity Report

AGENDA ITEM 9.1.1.1:	VOS Report

# SUMMARY

Please provide a summary of your talk highlighting key points (approximate length of a page to include in final report)

- SUMMARY:

The VOS Panel (VOSP) chairperson Mr. Henry Kleta reported on the activities of the Voluntary Observing Ship (VOS) Scheme, a network within the Ship Observations Team (SOT), during the last intersessional period.

VOS Panel - Terms of References

During SOT-10 and following that session the ToRs of the VOSP were adapted and updated.

The Voluntary Observing Ship (VOS) Panel shall:

- Review, recommend and coordinate the implementation of new and improved specialized shipboard meteorological instrumentation, siting and observing practices, as well as of associated software;

- Support the development and maintenance of new pilot projects;

- Oversee and encourage members to upgrade their VOS to report according to standards meeting climate user requirements, including reporting the required climate and ship parameters in both real time (GTS) and in delayed mode (via VOS GDAC);

- Develop and implement activities to optimize ship inspections and recruitment, including promotional material;

- Prepare annually a report on the status of VOS operations, data availability and data quality.

Action: Secretariats to ensure that the ToRs are stated correctly on all relevant websites and documents and are kept up-to-date. (Secretariats, asap and ongoing)

Activities of Chairperson during intersessional period

Regular SOT Tele-Conferences (Executive Board, Executive Committee, various Task Teams,...) were attended as well as several OCG Tele-Conferences (OCG Roundtable, Report Card,...).

Several meetings were attended in person or virtual:

- OCG 11

- CLIMAR 5

- E-Surfmar VOS Expert Team meetings (as Chair)

- PMO-6 workshop

- VOS discussions with Maersk

- GCW (Global Cryosphere Watch) / VOS discussions

- meetings of the WMO Study Group on the Global Basic Observing Network (SG-SGBON)

- SOT metadata internship at OceanOPS in 09/2020

The chairperson is attending SOT-11.

Performance of VOS network in 2020

VOS fleet

- Approx. 4200 VOS Stations were registered in the Pub47 metadata database end of 2020

- Approx. 2750 stations provided real-time observations to the GTS in 2020

  - plus ~4% compared to 2019

- ~10 % of the VOS fleet is automated

- 25 active VOS programmes provided VOS real-time data in 2020.

  - plus 2 programmes compared to 2019

Action: VOS operators are requested to keep their VOS metadata up-to-date in the relevant metadata database. (VOS operators, ongoig)

VOS real-time data (GTS, TAC or TDC)

- OceanOPS counts ~2.5 mill. VOS observations in the GTS in 2020

  - plus ~10% compared to 2019

- E-Surfmar Observation counters state ~ 2.8 mill. VOS observations in the GTS in 2020

Action: OceanOPS to implement functionality to allow output of information on number of observations (observation counters per selected station / stations / fleet) for a specified period of time (month / year). Furthermore, implement functionality to generate maps with only those observations on the map using VOS terminology. (OceanOPS, asap)

Recommendation: All VOS operators are invited to compare their observation counts with those from OceanOPS to find missing data and / or duplicates.

Recommendation: If data is drawn from GTS and re-ingested, the usage of special headers (making clear that these are duplicates or compilations) should be considered to allow easier identification of duplicates and / or original format or conversions made from the original observations.

VOS delayed mode data (IMMT)

- only 14 VOS programmes provided delayed mode data to the VOS GDACs in 2020

- only ~1.6 mill. IMMT observations were provided (only 60% of the 2020 VOS data!) to the VOS GDACs

Action: VOS operators are requested to provide quarterly delayed mode data to the VOS GDACs. (VOS operators, quarterly)

PMO network status (2020)

- ~45 PMOs were reported in 17 SOT annual reports

- a record low number of ship visits (~1000) were reported due to Covid19

- ~160 Port Meteorological Officers and Offices, providing service in 47 countries / territories, are listed in WMO No.9, Volume D, Part B (see https://community.wmo.int/activity-areas/operational-information-service/volume-d-information-shipping)

Action: All VOS operators and / or PMOs are requested to arrange provision of SOT annual reports via National Focal Point (VOS operators and PMOs, annually).

Action: Secretariats to provide easy access to NFP and PMO lists (with input from WMO and IOC members and keep them up-to-date, and link to them from relevant websites. (Secretariats, asap and ongoing)

VOS / Maersk

- The shipping company Maersk decided in 2019 to participate in the VOS network with all their company owned vessels (in total approx. 300 vessels).

- The VOSP chair acts as central focal point for Maersk concerning VOS.

- There are now 50 AWS stations (EUCAWS stations provided by DWD) installed on Maersk vessels.

- Maersk is planning to fully integrate the installed AWS into onboard systems (NMEA feed from AWS to ship systems)

- Additional ongoing discussions between DWD and Maersk concerning provision of historic data from Maersk ships to the VOS-GDAC operated by DWD in progress.

- Furthermore, potential to receive near real-time data feeds from Maersk owned system onboard their vessels for GTS ingestion under investigation.

SOT / VOS relevant websites:

  - VOS website

  - http://sot.jcommops.org/vos/

- Pub47 metadata database

  - http://www.jcommops.org/sot/vos_esurfmar/vosmetadata_v6/

- OceanOPS

  - https://www.ocean-ops.org/board?t=sot

- GOOS / SOT landing page

  - https://goosocean.org/sot

jcomm.info is offline, but many sites / documents link to jcomm.info content. This must be kept available and accessible.

ISO Project 23745 "General specification for shipboard meteorological instrument"

- approved by ISO committee ISO/TC 8/SC 13 (marine technology) in 2020 as new project in work programme of working group 2 "Ocean hydrometeorological observation"

- VOSP chair is the German delegate to ISO/TC 8/SC 13

- TT-ISC Chair and VOSP VC are involved in WG 2 as "contributor"

- no further progress to be reported

Action: Secretariats to organize replacement of outgoing VOSP VC as contributor to ISO&TC 8/SC 13/WG 2. (Secretariats, asap)

Development of the VOS network:

- Following SOT-9 the IMO MSC Circular 1293 “Participation in the WMO Voluntary Observing Ships (VOS) Scheme” was updated: MSC.1/Circ.1293/Rev.1 – 25 May 2018 (can be found on the VOS website)

- Draft Rev. MSC/Circ. 803 “Participation of NON-SOLAS Ships in the Global Maritime and Safety System (GMDSS)”:

(9) Non SOLAS ships operating in high sea areas are invited to participate in the WMO Voluntary Observing Ships (VOS) Scheme. […]

Circular is still in Draft status, therefore not publicly available.

Status of actions from SOT-10

| Ref. Item | Action Item | By | Deadline | Update |
| --- | --- | --- | --- | --- |
| A8.1/1 | Further explore and promote the possibility to auto-generate annual reports. | SOT-TC & VOS Chair | SOT-11 | ongoing |
| A8.1/2 | Develop documents on how to replace Call sign with SOT-ID and make it available for Ship operators. | VOS Chair & SOT-TC | August 2019 | pending |
| A10.1.2/2 | VOS chair to further revise the SOT ID allocation and come up with a revised version based on the ideas presented at the SOT-10. | VOS Chair & SOT-TC | Aug 2019 | pending |
| A10.1.2/3 | Prepare documentation on SOT ID transition and make them available on a central location for SOT community. | VOS Chair & SOT-TC | Dec 2019 | pending |
| A12.1.5/1 | Interested VOS operators to liaise with VOS chair to discuss participation/further steps of batch recruitment of Maersk ship. | VOS Operators | ASAP | ongoing |

### B. ACTIONS/DECISIONS/RECOMMENDATIONS REQUIRED:

Action: Secretariats to ensure that the ToRs are stated correctly on all relevant websites and documents and are kept up-to-date. (Secretariats, asap and ongoing)

Action: VOS operators are requested to keep their VOS metadata up-to-date in the relevant metadata database. (VOS operators, ongoing)

Action: OceanOPS to implement functionality to allow output of information on number of observations (observation counters per selected station / stations / fleet) for a specified period of time (month / year). Furthermore, implement functionality to generate maps with only those observations on the map using VOS terminology. (OceanOPS, asap)

Action: VOS operators are requested to provide quarterly delayed mode data to the VOS GDACs. (VOS operators, quarterly)

Action: All VOS operators and / or PMOs are requested to arrange provision of SOT annual reports via National Focal Point (VOS operators and PMOs, annually).

Action: Secretariats to provide easy access to NFP and PMO lists (with input from WMO and IOC members and keep them up-to-date, and link to them from relevant websites. (Secretariats, asap)

Action: Secretariats to organize replacement of outgoing VOSP VC as contributor to ISO&TC 8/SC 13/WG 2. (Secretariats, asap)

Recommendation: All VOS operators are invited to compare their observation counts with those from OceanOPS to find missing data and / or duplicates.

Recommendation: If data is drawn from GTS and re-ingested, the usage of special headers (making clear that these are duplicates or compilations) should be considered to allow easier identification of duplicates and / or original format or conversions made from the original observations.

(a)	Adopt draft Action/Decision 0.0.0/1 — Action/Decision title.

(b)	Adopt draft Recommendation 0.0.0/1 — Recommendation title.

# C. BACKGROUND INFORMATION (not to be included in the session report):

### References (if any):

1.	[Link to the full report on the website]

2.	...........

### Introduction

[Comment: Main points and arguments leading to formulation of draft decision presented in this document]

ANNEX XX

An Action/Decision  is an item directly related to SOT and on which SOT can action or decide directly. Details on rational for the action/decision should be included in the Background section.

A Recommendation involves proposed action(s)on another body outside of SOT (e.g. DBCP, JCOMM, WMO, IOC, CBS etc.). Rational for the Recommendation should be included in the Draft Recommendation.