# First session of the IODE Steering Group for PacMAN

# SG-PacMAN-I

# (PacMAN Advisory Board)

Online

14 September 2021

Annotated Agenda

Table of Contents

Executive Summary	2

Welcome and adoption of agenda	2

PacMAN work plan	2

PacMAN monitoring plan	4

PacMAN advisory board Terms of Reference, membership and Chair	5

Recommendations	5

Date and place of next session	6

Any other business	6

Closing of the session	6

Annex 1: Agenda and Time Table	6

Annex 2: List of participants	7

# Executive Summary

[To be added]

# Welcome and adoption of agenda

Mr Ward Appeltans, overall coordinator of the PacMAN project opened the meeting and introduced the meeting goals and agenda. He informed the board that all the information and documents of this meeting are available on IOC’s OceanExpert database via the following link: https://oceanexpert.org/event/3265. He then invited one person per organization to briefly present themselves and their team members. A group picture was taken.

Dr Ann-Katrien Leskrauwaet, representative of the Government of Flanders welcomed everyone and provided an introduction to the Flanders/UNESCO fund-in-trust to support UNESCO’s activities in the field of science, and why the PacMAN project was selected for funding. She thanked the government of Fiji for their support, and the University of the South Pacific and all the experts and stakeholders involved in PacMAN for their contribution to a successful implementation of PacMAN.

[name TBC], the representative of the Government of Fiji welcomed everyone and provided a brief overview of the government’s plans and efforts to address marine invasive species management in Fiji.

The PacMAN advisory board adopted the agenda with/without modification.

# PacMAN work plan

Mr Joape Ginigini (local PacMAN project manager) provided an overview of the PacMAN work plan and the status of the implementation (table, green = on track; orange = delayed and grey = not yet started).

|  |  | year 1 (Sept 2020 - Aug 2021) |  | year 2 (Sept 2021 - Aug 2022) |  | year 3 (Sept 2022 - Aug 2023) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | subactivity | S1 | S2 | S3 | S4 | S5 | S6 |
| Coordination and advisory board meetings |  |  |  |  |  |  |  |
|  | 1st advisory board meeting |  |  |  |  |  |  |
|  | 2nd advisory board meeting |  |  |  |  |  |  |
|  | 3rd advisory board meeting |  |  |  |  |  |  |
| Stakeholder forum, communication and outreach |  |  |  |  |  |  |  |
|  | Website, flyer, video |  |  |  |  |  |  |
|  | mailing list |  |  |  |  |  |  |
| Evaluation |  |  |  |  |  |  |  |
| Development of monitoring plan |  |  |  |  |  |  |  |
|  | review technology |  |  |  |  |  |  |
|  | review sampling and sampling processing protocols |  |  |  |  |  |  |
|  | select species |  |  |  |  |  |  |
|  | data management plan |  |  |  |  |  |  |
|  | data policy |  |  |  |  |  |  |
|  | design sampling campaigns |  |  |  |  |  |  |
|  | costing overview |  |  |  |  |  |  |
| Scientific training |  |  |  |  |  |  |  |
|  | capacity assessment |  |  |  |  |  |  |
|  | development of training content |  |  |  |  |  |  |
|  | training course for scientists |  |  |  |  |  |  |
|  | training course for stakeholders |  |  |  |  |  |  |
| Field and lab work |  |  |  |  |  |  |  |
|  | test phase |  |  |  |  |  |  |
|  | operational phase |  |  |  |  |  |  |
| Development of infrastructure, bioinformatics pipeline and reference database |  |  |  |  |  |  |  |
|  | Development of a bioinformatics pipeline to calculate amplicon sequence variants (ASVs) from raw reads generated by next- generation sequencing (NGS) platforms, and package these together with standardized metadata into Darwin Core Archives. |  |  |  |  |  |  |
|  | Development of sequence reference databases and/or enhancement of existing reference databases and alignment with the World Register of Marine Species (WoRMS). |  |  |  |  |  |  |
| Development of decision support tool |  |  |  |  |  |  |  |
|  | Development and evaluation of habitat suitability models based on OBIS occurrences of potentially invasive species. |  |  |  |  |  |  |
|  | Development of risk assessment algorithms to inform policy of species that are likely to establish themselves and become invasive in a particular location. |  |  |  |  |  |  |
|  | Development of a dashboard application and alerting system to display and disseminate information produced by the risk assessment component. |  |  |  |  |  |  |

# PacMAN monitoring plan

The PacMAN monitoring plan is the output of one year of work and consultations with scientists and local stakeholders. It presents the sampling and data processing activities for the next two years of the project. Dr Saara Suominen, PacMAN scientific officer, provided a summary of the plan. The draft monitoring plan was shared with the members of the board and introduction videos were made on the topics listed below, in order to provide enough time to review and provide input. The introduction videos can be viewed via the following YouTube links:

- Introduction of the objectives: https://youtu.be/9aTdTynjM00

- Target species: https://youtu.be/Ppcvqr-3F5Q

- Sampling design/protocols: https://youtu.be/opVnw5X7pfo

- Data management plan: https://youtu.be/It3vJbrBUC8

The PacMAN advisory board welcomed the PacMAN monitoring plan and fully endorsed the execution of the activities.

# PacMAN advisory board Terms of Reference, membership and Chair

Because this is the first meeting of the full PacMAN advisory board, the Terms of Reference, membership and chair of the board have been discussed and approved.

Mr Appeltans reminded the group that being an IODE project, the advisory board is officially called the IODE Steering Group for PacMAN (SG-PacMAN).

The SG-PacMAN proposed the following Terms of Reference:

- The SG-PacMAN will act as the project advisory body, i.e.

  - Provide advice to the PacMAN work plan, the monitoring plan as well as the decision-support tool and,

  - Help raise awareness of the outcomes and support the uptake of the PacMAN services at local and regional level.

The membership of the SG-PacMAN is composed of:

- SG-PacMAN chair

- Project coordinator

- Local project manager

- Systems engineer

- Scientific experts

- Representatives of major stakeholders/users from national, regional and international organizations and

- Representatives of the donor.

We received the following nomination(s) for chair of the PacMAN advisory board: [name].

The SG-PacMAN adopted the terms of reference and membership and welcomed the appointment of [name] as the chair.

# Recommendations

The PacMAN advisory board proposed the following recommendations and action items for consideration by the project team:

[add list]

# Date and place of next session

The next PacMAN advisory board meeting will take place on [date] and will be held [face-to-face or online].

# Any other business

# Closing of the session

The first session of the IODE Steering Group for PacMAN (PacMAN advisory board) concluded on 14 September 2021 at [time].

# Annex 1: Agenda and Time Table

Fiji Standard Time (GMT +12)

| 7:00 PM - 7:40 PM | Welcome and adoption of agenda |
| --- | --- |
| 7:40 PM - 7:50 PM | PacMAN work plan |
| 7:50 PM - 8:20 PM | PacMAN monitoring plan |
| 8:20 PM - 8:35 PM | PacMAN advisory board Terms of Reference, membership and Chair |
| 8:35 PM - 8:50 PM | Recommendations |
| 8:50 PM - 8:55 PM | Date and place of next session |
| 8:55 PM - 9:00 PM | Any other business |
| 9:00 PM | Closing of the session |

# Annex 2: List of participants

Donor/Flanders Government

Ms. Ann-Katrien LESCRAUWAET

Director International Relations

International Relations

Vlaams Instituut voor de Zee

Wandelaarkaai 7

8400 Oostende

Belgium

Tel: +32475493452

Email: annkatrien.lescrauwaet@vliz.be

Mr. Gert VERREET

Policy Advisor

Vlaamse Overheid - Departement Economie, Wetenschap & Innovatie, Afdeling Onderzoek

Koning Albert II-laan 35 bus 10

1000 Brussel

Belgium

Tel: +32 499 59 49 83

Email: gert.verreet@ewi.vlaanderen.be

Fijian Authorities/local stakeholders

Mr. Nitesh DATT

Agriculturist/ Plant Pathologist/ Molecular diagnostics

Biosecurity Authority of Fiji

Suva

Suva

Fiji

Tel: +679 9278638

Email: ndatt@baf.com.fj

Mr. Chaminda DISSANAYAKE

Senior Veterinary Officer

Biosecurity Authority of Fiji

Level 3, Provident Plaza I, Ellery Street

Suva

Fiji

Email: chaminda@baf.com.fj

Senivasa WAQAIRAMASI

Department of Environment – Ministry of Local Government

Fiji

Email: Senivasa.waqairamasi@govnet.gov.fj

Regional/International Stakeholders

Mr. John ALONSO

Project Technical Analyst

Marine Environment Division

International Maritime Organization

4 Albert Embankment

London

SE1 7SR

United Kingdom

Email: jalonso@imo.org

Mr. Nic BAX

Oceans&Atmosphere

CSIRO Oceans and Atmosphere Information and Data Centre, Hobart

GPO Box 1538

Hobart TAS 7001

Australia

Tel: +61 3 6232 5341

Email: Nic.Bax@csiro.au

Mr. Henrik ENEVOLDSEN

Head of Centre, IOC UNESCO Programme Coordinator, Technical Secretary IPHAB

IOC Science and Communication Centre on Harmful Algae

IOC Science and Communication Centre on Harmful Algae

Universitetsparken 4

University of Copenhagen, Dept of Biology, Marine Biological Section

2100 Ø Copenhagen

Denmark

Tel: +45 23260246

Email: h.enevoldsen@unesco.org

Ms. Molly POWERS

Team Leader, Ocean Literacy and Maritime Capacity

Oceans & Maritime Programme

Secretariat of the Pacific Community - Regional Office

Ratu Mara Road

Private Mail Bag

Suva

Fiji

Tel: +6798629655

Email: mollyp@spc.int

Ms. Katy SOAPI

Manager

Pacific Community Centre for Ocean Science

Secretariat of the Pacific Community - Regional Office

Ratu Mara Road

Private Mail Bag

Suva

Fiji

Email: katy.soapi@gmail.com

Scientific Experts

Mr. Pier Luigi BUTTIGIEG

Data Scientist

Helmholtz Metadata Collaboration

GEOMAR | Helmholtz Centre for Ocean Research Kiel

Duesternbrooker Weg 20

24105 Kiel

Germany

Tel: +494212028984

Email: pier.buttigieg@awi.de

Mr. Neil DAVIES

Director

UC Gump South Pacific Research Station

BP-244

UCB

98728 Maharepa Moorea

French Polynesia

Email: ndavies@berkeley.edu

Mr. Pascal HABLÜTZEL

Scientist

Research Department

Vlaams Instituut voor de Zee

Wandelaarkaai 7

8400 Oostende

Belgium

Tel: +34 59341416

Email: pascal.hablutzel@vliz.be

Mr. Kevin MACKAY

Marine Data Manager

Environmental Information

National Institute of Water and Atmosphere

Private Bag 99940, Newmarket

Wellington

Auckland 1149

New Zealand

Tel: +64 4386 0300

Email: k.mackay@niwa.co.nz

Mr. Christopher MEYER

Research Zoologist and Curator

Invertebrate Zoology

National Museum of Natural History, Smithsonian Institution

12th and Constitution Ave., NW

Washington DC, 20560-0163

United States

Tel: +1 202-633-1752

Email: meyerc@si.edu

Mr. Matthias OBST

Scientist

Department of Marine Sciences

Göteborg University, Department of Marine Ecology

Box 461

40530 Gothenburg

Sweden

Tel: +46 (0) 76 618 3827

Email: matthias.obst@marine.gu.se

Mr. Craig SHERMAN

Associate Professor

School of Life and Environmental Sciences

Deakin University

Deakin University, Pigdons Road

Waurn Ponds VIC 3216

Australia

Tel: +61 (3) 52271406

Email: csherman@deakin.edu.au

PacMAN project coordination team

Mr. Ward APPELTANS

Project Manager OBIS, GOOS Biology & Ecosystems, IOC Capacity Development

UNESCO / IOC Project Office for IODE

Wandelaarkaai 7

Pakhuis 61

8400 Oostende

Belgium

Tel: +32 59 34 01 76

Email: w.appeltans@unesco.org

Ms. Gilianne BRODIE

Deputy Director IAS

Institute of Applied Sciences

University of the South Pacific, Faculty of Science Technology & Environment, Institute of Applied Sciences

Lower Laucala Campus

Suva

Fiji

Tel: +679 3232876 or 679 3232965 (IAS main office)

Email: gilianne.brodie@usp.ac.fj

Mr. Joape GINIGINI

Senior Scientific Officer and Local Project Manager, PNPRC

Institute of Applied Sciences

University of the South Pacific, Faculty of Science Technology & Environment, Institute of Applied Sciences

Lower Laucala Campus

Suva

Fiji

Tel: 679 7189693

Email: jginigini@yahoo.com

Ms. Paayal KUMAR

Researcher

Institute of Applied Sciences

University of the South Pacific, Faculty of Science Technology & Environment, Institute of Applied Sciences

Lower Laucala Campus

Suva

Fiji

Tel: +6797328408

Email: paayalkumar7@gmail.com

Mr. Pieter PROVOOST

OBIS Data Manager

UNESCO / IOC Project Office for IODE

Wandelaarkaai 7

Pakhuis 61

8400 Oostende

Belgium

Tel: +32 59 340161

Email: p.provoost@unesco.org

Ms. Saara SUOMINEN

Scientific Officer

OBIS

UNESCO / IOC Project Office for IODE

Wandelaarkaai 7

Pakhuis 61

8400 Oostende

Belgium

Email: s.suominen@unesco.org