**TASK TEAM ON TSUNAMI EXERCISE – PLAN OF ACTION 2022**

**CO-CHAIR:** Ceren Ozer Sozdinler (Gebze Technical University Department of Civil Engineering, Turkey), Marinos Charalampakis (National Observatory of Athens/ Greece)

| **Strategic Area** | **Activity** | **Time Frame** | **Responsible Per/ Inst** |
| --- | --- | --- | --- |
| **Task Team on Tsunami Exercise** | Submission of the final version of the Evaluation Report of NEAMWave21 | February 2022 | TT-TE co-chairs, exercise team & IOC Secretariat |
| Planning of NEAMWave23 | Whole intersessional period | TT-TE co-chairs, exercise team & IOC Secretariat |
| Having online meetings with DG-ECHO and CPA representatives | March - April 2022 | TT-TE co-chairs, WG-04 & IOC Secretariat |
| Request Civil Protection Authorities with exercises experience to prepare a one-page guiding document to share with other non-experienced CPAs, describing their experience in implementing Phase B of NEAMWave Exercises | April - May 2022 | TT-TE co-chairs, exercise team & IOC Secretariat |
| Work together with the Secretariat to prepare a concept information paper to inform CPAs about the general concept of NEAMWave | May 2022 | TT-TE co-chairs, exercise team & IOC Secretariat |
| Revision of online tools (subscription & evaluation) | September – October 2022 | TT-TE co-chairs, exercise team & IOC Secretariat |
| Having online meetings with DG-ECHO and CPA representatives | October - November 2022 | TT-TE co-chairs, WG4 & IOC Secretariat |