## Slide 1
Working Group 4
Public Awareness, Preparedness and Mitigation
Draft Plan of action for 2022
Steering Committee meeting 9-11 April 2022
Chair
Cecilia Valbonesi
(University of Florence, Italy)

## Slide 2: Objective: Promote community preparedness and initiatives at national level and in the framework of international projects, fostering synergies whenever possible
Activity
Target/Result indicators
Interact with the TT on Tsunami Ready
-Participate in Tsunami Ready TT meetings
-With TT on Tsunami Ready:
- Organize a workshop on methodologies to define inundation areas and how to communicate to local stakeholders (in cooperation with WG1);
- Promote discussion on alert dissemination methodologies;
-Organize webinar to enhance the development of TR in NEAM region and gain experience by interacting with experts from other ICGs.
Monitoring of TR pilot projects in NEAM area and sharing with WG4 members

## Slide 3: Objective: Promote community preparedness and initiatives at national level and in the framework of international projects, fostering synergies whenever possible
Activity
Target/Result indicators
Organize an online roundtable on ongoing studies in different Countries
Share the State members activities (see next slides):
I received updates from:
Elena Giusta from ISPRA, Italy
Alessandro Amato and Lorenzo Cugliari from INGV, Italy
Luis Matias from Instituto D. Luiz, Portugal
Marzia Santini, JRC, EU
Enhance the assessment of the tsunami risk perception in NEAM region

## Slide 4
ISPRA ACTIVITIES IN WG4:
Updated the SiAM (Italian tsunami Alert System) web page with the report of the last ICG/NEAMTWS assembly and another on the Tsunami READY programme:
https://www.isprambiente.gov.it/it/servizi/sistema-nazionale-di-allerta-maremoti-1
Tsunami Ready programme was explained in this bulletin: https://www.isprambiente.gov.it/files2021/pubblicazioni/periodici-tecnici/prue/prue-03-2021.pdf
In next slide the news about Tsunami Awareness Day (November 5 2021)
ITALIAN ACTIVITIES IN PUBLIC AWARENESS, PREPAREDNESS AND MITIGATION

## Slide 5
5 novembre: nel mondo si celebra lo Tsunami Day
I maremoti sono eventi rari, ma possono accadere con effetti disastrosi. Negli ultimi 100 anni, 58 eventi hanno causato più di 260.000 vittime, superando qualsiasi altro rischio naturale a livello globale. Nel prossimo decennio, circa la metà della popolazione mondiale vivrà su terre sempre più esposte a calamità naturali, ivi compresi i maremoti, per i quali è importante adottare piani di riduzione degli impatti.
Nel dicembre 2015, l'Assemblea Generale delle Nazioni Unite ha designato il 5 novembre come “Giornata mondiale della consapevolezza del rischio di tsunami” invitando i governi, gli organismi internazionali e le associazioni della società civile a sensibilizzare l'opinione pubblica sulla gestione delle misure di mitigazione, grazie anche a soluzioni tecnologiche sempre più innovative nei sistemi di allerta rapida.
L’ISPRA che, con la sua rete di stazioni di rilevamento dell’innalzamento del mare, è una componente, del Sistema nazionale di Allerta maremoti (SiAM), contribuisce anche all’attuazione del programma Tsunami Ready, nell’ambito del Gruppo di coordinamento intergovernativo per il sistema di allarme rapido e mitigazione degli tsunami nell'Atlantico nord-orientale, nel Mediterraneo e nei mari connessi (ICG/NEAMTWS) della Commissione Intergovernativa Oceanografica dell’UNESCO.
Il programma Tsunami Ready supporta le comunità costiere nell’adozione delle più idonee misure di preparazione a possibili maremoti, di piani di gestione del rischio e di mitigazione degli effetti di tali eventi.

## Slide 6
INGV ACTIVITY FOR NEAM WG4
In the framework of the WG4 Action Plan for the 2022 and in the broader perspective of the Decade Tsunami Programme, the INGV Tsunami Alert Center is working to disseminate tsunami risk and increase public knowledge and awareness.
PUBLIC OUTREACH ACTIVITIES TSUNAMI ALERT CENTER
Among the dissemination and public outreach tools implemented by the INGV Tsunami Alert Center there is the website, closely interconnected with other INGV communication channels including the blog "INGVterremoti" and social pages (Twitter and Facebook).
The website adopted a multidisciplinary, didactic/scientific approach that privileges graphic and textual communication through discursive sections that guide the user in a cognitive learning path. The website and the contents of updates in it are made in two languages: Italian/English.
Education activity:
Minturno:
On March 24, 2022, an outreach meeting with students from the high school of Leon Battista Alberti High School was carried out in the Municipality of Minturno.
Tivoli:
CAT-INGV researchers carried out a first dissemination meeting with Lazzaro Spallanzani high school students in Tivoli (RM). The meeting aims to inform students about the tsunami risk in Italy and in the Mediterranean Sea and to improve the topic knowledge in order to provide insights and identify the best communication channels for young people.
Tsunami risk perception issue:
The meetings carried out in both schools started with the Tsunami Risk Perception questionnaire administration. The web-based questionnaire was administered through the Google Form platform and maintained the same structure used for the CATI methodology survey (Cerase et al., 2019; Cugliari et al., 2021).
(see Communication, outreach activities and tsunami risk perception in Italy. A starting point and the perspectives of the INGV Tsunami Alert Center-report in appendix)

## Slide 7: ACTIVITIES IN PUBLIC AWARENESS, PREPAREDNESS AND MITIGATION
PORTUGAL:
A siren system in Cascais is being upgraded and it will start the tests soon.
- Portugal activities have been mostly concerned with the improved monitoring of tsunamis that submarine cables might bring.

## Slide 8: ACTIVITIES IN PUBLIC AWARENESS, PREPAREDNESS AND MITIGATION
JRC:
Managed to complete the evaluation report of the Tsunami Last Mile exercise performed in Malta on 5 November 2021 (see the Tsunami Last Mile-MALTA21 exercise Marsaxlokk (Malta), 5 November 2021 Evaluation team, 5 April 2022 - DRAFT Evaluation report in appendix).

## Slide 9: Objective : Encourage and support the development of the donwnstream (Preparedness and Response) component of the ICG/NEAMTWS programme
Activity
Target/Result indicators
Discussion on legal implications of piloting Tsunami Ready-like initiatives in some test Countries of the NEAM region
-Share the study on the impact of TR guidelines on the responsibilities of the local and the national TR board members.
- Study on the UNESCO’s role in the recognition of a municipality as TR

## Slide 10
Objective: Information and experience exchange regarding tsunami risk and disaster management within NEAM region
Activity
Target/Result indicators
Attempt to collaborate with the TSPs to obtain inputs (e.g. reports) in order to contribute to keeping the NEAMTIC website updated and to enriching its content
-Contacts with all TSPs by a periodical email (two months)
-Welcome and develop Doctor Didem Samut Cambaz’s proposal about emphasizing - as a paragraph or link in the NEMATIC web page - the first decade of the NEAMTWS TSPs

## Slide 11: Objective :Enhancing interdisciplinarity in tsunami risk and disaster management
Activity
Target/Result indicators
To explore contributions and views of social scientists on tsunami threat levels.
The research will be conducted by Andrea Cerase and Lorenzo Cugliari, Italy):
-A first step analysis (short report) was presented by Professor Andrea Cerase during 17th Session of the Intergovernmental Coordination Group for the Tsunami Early Warning and Mitigation System in the North-eastern Atlantic, the Mediterranean and Connected Seas (Online)
24 - 26 November 2021
- The study will hopefully be completed until the end of 2022

## Slide 12: Objective : Representation of WG4 in ICG/NEAMTWS and in INTER-ICG TOWS TASK TEAM on DMP (Disaster Management and Preparedness)
Represent WG4 at the meeting of the Inter-ICG Task Team on “Disaster management and preparedness”, February 2022
Share the WG4 plan of action for 2022 with the NEAMTWS members in February 2022
Report progress to the next ICG
Activity
Target/Result indicators
Share the most relevant issues of Inter-ICG Task Team on “Disaster management and preparedness” with WG4 members (in cooperation with TT on Tsunami Ready, regarding TR activities)
Report to the ICG
Participation to the SC meeting/WG4 presentation
Draft PoA for WG4

## Slide 13: Objective : Cooperation with other WGs and TTs (TT on tsunami exercises, WG1, TT on documentation)
Activity
Support when needed and provide feedbacks
Participation to online meetings, input/provide feedbacks to reference documents upon request
Target/Result indicators