## TR
UNESCO/IOC Tsunami Ready Recognition Programme
Name of Community
Update Date: 14 March 2023
Indicators & Actions | Target Completion (Date) | In Progress (Date) | Completed (Date) | Lead (agency, person) | Notes
NTRB
ASSESSMENT (ASSESS)
ASSESS-1. Tsunami hazard zones are mapped and designated
Maps and Products |  |  | 2023-03-31 | Univ. Montpellier 3 (F. Leone), Univ. El Jadida (S. Mellas), Univ. of Lisbon (R. Omira) Univ. El Jadida (K. Elkhalidi) Univ. El Jadida (B. Zourarah) | Done
Report |  | 2023-05-30 |  | Univ. Montpellier 3 (F. Leone), Univ. El Jadida (S. Mellas), Univ. of Lisbon (R. Omira) Univ. El Jadida (K. Elkhalidi) Univ. El Jadida (B. Zourarah) | scheduled to be completed by 30/06/2023
ASSESS-2. The number of people at risk in the tsunami hazard zone is estimated
Identification of Lead |  |  | 31/03/2023 | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone)
Census data residents |  |  |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 30/06/2023
Census visitors |  | X |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 30/06/2023
Community validation |  |  |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 30/06/2023
ASSESS-3. Economic, infrastructural, political, and social resources are identified
Identification of Lead |  |  | 31/03/2023 | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone)
List of resources |  | X |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 30/06/2023
PREPAREDNESS (PREP)
PREP-1. Easily understood tsunami evacuation maps are approved.
Identification of Lead | 2023-01-01 |  |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone)
Data layers: Infrastructures, roads, etc. |  |  | 30/05/2023 | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 30/06/2023
Design and create Evacuation Map |  |  | 30/05/2023 | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 30/06/2023
Evacuation Map text (Backside) |  |  | 30/05/2023 | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 30/06/2023
Approval of Evacuation Map (official) |  | X |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 30/06/2023 The maps are sent to the stakeholders for their approval
Printing of Tsunami Evacuation Map |  | X |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | scheduled to be completed by 20/09/2023
Distribution of Tsunami Evacuation Map |  | X |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone) | storymap on line scheduled to be completed by 30/09/2023
PREP-2. Tsunami information including signage is publicly displayed.
Identification of Lead | 2023-03-31 |  |  | Univ. El Jadida (K. Elkhalidi) & Univ. El Jadida (B. Zourarah) | scheduled to be started by 01/09/2023
Decide Type and artwork for Tsunami Signage / Public Displays | 2023-09-01 |  |  |  | scheduled to be started by 01/09/2023
Signage / Public Displays Site Plan | 2023-09-01 |  |  |  | scheduled to be started by 01/09/2023
Identification of Supplier and Quotes for Signage / Public Displays | 2023-09-01 |  |  |  | scheduled to be started by 01/09/2023
Procurement of Signage / Public Displays | 2023-10-01 |  |  |  | scheduled to be started by 01/09/2023
Installation of SIgnage / Public Displays | 2023-10-01 |  |  |  | scheduled to be started by 01/09/2023
PREP-3. Outreach and public awareness and education resources are available and distributed.
Identification of Lead |  |  |  | Univ. El Jadida (K. Elkhalidi) & Univ. El Jadida (B. Zourarah)
Websites / Social Media |  |  |  |  | scheduled to be started by 01/07/2023
Brochures / Flyers |  |  |  |  | scheduled to be started by 01/07/2023
Radio and Television |  |  |  |  | scheduled to be started by 01/07/2023
Newspaper and Newsletter |  |  |  |  | scheduled to be started by 01/07/2023
Videos |  |  |  |  | scheduled to be started by 01/07/2023
Bulk e-mail |  |  |  |  | scheduled to be started by 01/07/2023
Other:
PREP-4. Outreach or educational activities are held at least 3 times a year.
Identification of Lead | 2023-03-31 |  |  | Univ. El Jadida (K. Elkhalidi) & Univ. El Jadida (B. Zourarah)
Community tsunami safety workshops, town hall, or similar public / private meetings. | 2023-09-01 |  |  |  | scheduled to be started by 01/09/2023
Booth at community events and/or county fairs. | 2023-09-01 |  |  |  | scheduled to be started by 01/09/2023
Other:
PREP-5. A community tsunami exercise is conducted at least every two years
Identification of Lead | 2023-03-31 |  |  | Univ. El Jadida (K. Elkhalidi) & Univ. Montpellier 3 (F. Leone)
Planning | 2023-09-01 |  |  |  | scheduled to be started by 01/09/2023
Conduct |  |  |  |  | scheduled to be completed by 04/11/2023
Evaluation |  |  |  |  | scheduled to be completed by 04/11/2023
RESPONSE (RESP)
RESP-1. A community tsunami emergency operations plan is approved.
Identification of Lead
Plan should include (requirements): |  |  |  |  | scheduled to be started by 01/09/2023
Tsunami hazard and risk assessment
Tsunami-hazard profile, including source locations, extend of inundation, run-up, previous or future tsunamis
Community vulnerability
Detailed 24-hour warning point procedures
Emergency operations center (EOC) activation criteria
Tsunami criteria and procedures for the activation of the public warning system
Contact information for all jurisdictional agencies and response partners
Evacuation plans for tsunamis, roles of community entities/agencies, maps and protocols
Procedures for updating information and determine when evacuated zones are safe
Procedures for providing security for the evacuated zone(s)
Procedures for reporting tsunami impacts in the community.
Schools and critical facilities in the emergency operations plan
Approval Tsunami Response Plan
RESP-2. The capacity to manage emergency response operations during a tsunami is in place.
Identification of Lead
Has a 24-hour operations or plan to activate an EOC for tsunami incidents |  |  |  |  | scheduled to be started by 01/01/2024
Has warning reception and dissemination capability
Has ability and authority to activate the public warning system in its area of responsability
Maintains the ability to communicate within and across jurisdictions
RESP-3. Redundant and reliable means (for community) to timely receive 24-hour official tsunami alerts are in place.
Identification of Lead
Method 1 |  |  |  |  | scheduled to be started by 01/01/2024
Method 2
Method 3
Other:
RESP-4. Redundant and reliable means (for community) to timely disseminate 24-hour official tsunami alerts to the public are in place.
Identification of Lead
Method 1 |  |  |  |  | scheduled to be started by 01/01/2024
Method 2
Method 3
Other: