## TR
UNESCO/IOC Tsunami Ready Recognition Programme
Büyükçekmece - Türkiye
Update Date: 30 May 2023
Indicators & Actions | Target Completion (Date) | In Progress (Date) | Completed (Date) | Lead (agency, person) | Notes
NTRB
ASSESSMENT (ASSESS)
ASSESS-1. Tsunami hazard zones are mapped and designated |  |  |  | IMM &METU | https://depremzemin.ibb.istanbul/guncelcalismalarimiz/#le-tsunam-blg-ktapiklari
Maps and Products |  |  | 2022
Report |  |  | 2022
ASSESS-2. The number of people at risk in the tsunami hazard zone is estimated |  |  |  | IMM &METU
Identification of Lead |  |  |  | IMM &METU
Census data residents |  |  | 2022
Census visitors |  | 2023 |  |  | One million people, summertime, Sunday
Community validation |  | 2023 |  |  | not yet
ASSESS-3. Economic, infrastructural, political, and social resources are identified |  |  |  | IMM &METU
Identification of Lead |  |  | 2023 | IMM &METU
List of resources |  |  | 2023 |  | Done
PREPAREDNESS (PREP)
PREP-1. Easily understood tsunami evacuation maps are approved. |  |  | 2022 | METU | Approved
Identification of Lead |  |  | 2022 | METU
Data layers: Infrastructures, roads, etc. |  |  | 2022 |  | Report Completed
Design and create Evacuation Map |  |  | 2022 |  | Report Completed
Evacuation Map text (Backside) |  |  | 2022 |  | Report Completed
Approval of Evacuation Map (official) |  |  | 2022 |  | Report Completed
Printing of Tsunami Evacuation Map |  |  | 2022 |  | Report Completed
Distribution of Tsunami Evacuation Map |  |  | 2022 |  | Available in the web: https://depremzemin.ibb.istanbul/guncelcalismalarimiz/#le-tsunam-blg-ktapiklari
PREP-2. Tsunami information including signage is publicly displayed. |  |  | 2022 | IMM | Completed
Identification of Lead |  |  | 2022 | IMM
Decide Type and artwork for Tsunami Signage / Public Displays |  |  | 2022
Signage / Public Displays Site Plan |  |  | 2022
Identification of Supplier and Quotes for Signage / Public Displays |  |  | 2022
Procurement of Signage / Public Displays |  |  | 2022
Installation of SIgnage / Public Displays |  |  | 2022
PREP-3. Outreach and public awareness and education resources are available and distributed. |  |  | 2022 | KOERI & METU | Ongoing
Identification of Lead |  |  |  | KOERI & METU
Websites / Social Media | May-June | Feb - March |  | KOERI & METU
Brochures / Flyers | May-June | Feb - March |  | KOERI & METU
Radio and Television | May-June | Feb - March |  | KOERI & METU
Newspaper and Newsletter | May-June | Feb - March |  | KOERI & METU
Videos | May-June | Feb - March |  | KOERI & METU
Bulk e-mail
Other:
PREP-4. Outreach or educational activities are held at least 3 times a year. |  |  |  | KOERI & METU | Ongoing
Identification of Lead |  |  |  | KOERI & METU | We performed a meeting at Büyükçemece Anatolian High School. We made presentations on Tsunami, disseminated outreach material and replied the questions of the students in order to increase the awarness on Tsunami specifically in Marmara region. We made another meeting at the Büyükçekmece Municipality at the 15th March. We made presentations for the stakeholders in Istanbul (Safe Guard Commander, Büyükçekmece Municipality, İstanbul Metropolitan Municipality were some of the attendees to this meeting.)
Community tsunami safety workshops, town hall, or similar public / private meetings. | May-June | Feb - March |  | KOERI & METU | We will have another meeting on 1th June at the Cevdet Zebure Kotan primary school. We will be presenting outreach material which is prepared specifically fro that age group. We will be presenting some cartoons on the Earthquake and Tsunami. We will perform another meeting with the Büyükçekmece Municipality to discuss the possible SOP.
Booth at community events and/or county fairs. | May-June | Feb - March |  | KOERI & METU
Other:
PREP-5. A community tsunami exercise is conducted at least every two years |  |  |  | KOERI | NEAMWave23
Identification of Lead |  |  | 2022 | KOERI | WTAD 2022 COMPLETED
Planning |  |  | 2022 | KOERI & METU
Conduct |  |  | 2022 | KOERI & METU IMM & AFAD
Evaluation |  |  | 2022
RESPONSE (RESP)
RESP-1. A community tsunami emergency operations plan is approved. |  |  |  | KOERI & METU AFAD & NTRB | NTRB was established for Türkiye. However, at first due to the devastating earthquake activity in Eastern Turkiye, and later on because of the Presesential and Parliamentary elections in the country, we couldn't progress much on the establishment of TRLC and SOP. We are trying to set a date for the new meeting in which the execution of NEAMWave2023 will also be discussed. Now, we hope that we will be able to continue working on TRLC and SOP's more effectively.
Identification of Lead | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Plan should include (requirements): | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Tsunami hazard and risk assessment | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Tsunami-hazard profile, including source locations, extend of inundation, run-up, previous or future tsunamis | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Community vulnerability | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Detailed 24-hour warning point procedures | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Emergency operations center (EOC) activation criteria | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Tsunami criteria and procedures for the activation of the public warning system | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Contact information for all jurisdictional agencies and response partners | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Evacuation plans for tsunamis, roles of community entities/agencies, maps and protocols | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Procedures for updating information and determine when evacuated zones are safe | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Procedures for providing security for the evacuated zone(s) | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Procedures for reporting tsunami impacts in the community. | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Schools and critical facilities in the emergency operations plan | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Approval Tsunami Response Plan |  | 2023
RESP-2. The capacity to manage emergency response operations during a tsunami is in place. |  | 2023 |  | KOERI & METU AFAD & NTRB
Identification of Lead | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Has a 24-hour operations or plan to activate an EOC for tsunami incidents | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Has warning reception and dissemination capability | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Has ability and authority to activate the public warning system in its area of responsability | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Maintains the ability to communicate within and across jurisdictions | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
RESP-3. Redundant and reliable means (for community) to timely receive 24-hour official tsunami alerts are in place. |  | 2023 |  | KOERI
Identification of Lead | May-June | Feb - March |  | KOERI & METU AFAD & NTRB | Some methods already in place / need for a review
Method 1- | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Method 2- | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Method 3 | May-June | Feb - March |  | KOERI & METU AFAD & NTRB
Other:
RESP-4. Redundant and reliable means (for community) to timely disseminate 24-hour official tsunami alerts to the public are in place. |  | 2023
Identification of Lead | May-June | Feb - March |  | KOERI & METU AFAD & NTRB | Some methods already in place / need for a review
Method 1 | May-June | Feb - March |  | KOERI & METU AFAD & NTRB | Email
Method 2 | May-June | Feb - March |  | KOERI & METU AFAD & NTRB | Fax
Method 3 | May-June | Feb - March |  | KOERI & METU AFAD & NTRB | Sms
Other: