## TR
UNESCO/IOC Tsunami Ready Recognition Programme
Larnaca
Update Date: 1 June 2023
Indicators & Actions | Target Completion (Date) | In Progress (Date) | Completed (Date) | Lead (agency, person) | Notes
NTRB
ASSESSMENT (ASSESS)
ASSESS-1. Tsunami hazard zones are mapped and designated | July 2023 |  |  | GSD
Maps and Products | July 2023 | December 2022 |  |  | Tender NOA INGV and IHC
Report | July 2023 | December 2022
ASSESS-2. The number of people at risk in the tsunami hazard zone is estimated | December 2023
Identification of Lead | December 2022 | February 2023 |  |  | Partner - CUT (Cyprus University of Technology)
Census data residents | December 2023 | March 2023
Census visitors | December 2023 | March 2023
Community validation | December 2023 | March 2023
ASSESS-3. Economic, infrastructural, political, and social resources are identified |  |  |  |  | Partner - CUT (Cyprus University of Technology)
Identification of Lead | December 2022 | February 2023
List of resources | February 2024 | February 2023
PREPAREDNESS (PREP)
PREP-1. Easily understood tsunami evacuation maps are approved. | November 2023 |  |  | GSD | Aproval through WORKSHOP by NTRB
Identification of Lead | December 2022 | December 2022
Data layers: Infrastructures, roads, etc. | February 2023 | February 2023 |  |  | Tender NOA INGV and IHC
Design and create Evacuation Map | September 2023 | February 2023
Evacuation Map text (Backside) | September 2023 | February 2023
Approval of Evacuation Map (official) | November 2023 | February 2023 |  |  | Workshop In larnaca NOA INGV and IHC
Printing of Tsunami Evacuation Map | November 2023 | February 2023 |  |  | GSD/Larnaca Municipality
Distribution of Tsunami Evacuation Map | December 2023 | February 2023
PREP-2. Tsunami information including signage is publicly displayed. | February 2024 |  |  | GSD, NTRB
Identification of Lead | February 2023 | February 2023 |  |  | Civil Defence/Larnaca Municipality
Decide Type and artwork for Tsunami Signage / Public Displays | November 2023 | February 2023 |  |  | GSD, NTRB
Signage / Public Displays Site Plan | November 2023 | February 2023 |  |  | Civil Defence/Larnaca Municipality
Identification of Supplier and Quotes for Signage / Public Displays | December 2023 | February 2023
Procurement of Signage / Public Displays | January 2024 | February 2023
Installation of SIgnage / Public Displays | March 2024 | February 2023
PREP-3. Outreach and public awareness and education resources are available and distributed. | December 2023 |  |  | GSD, NTRB
Identification of Lead | February 2023 | February 2023 |  |  | Civil Defence/Larnaca Municipality
Websites / Social Media | February 2024 | February 2023
Brochures / Flyers | February 2024 | February 2023
Radio and Television | February 2024 | February 2023
Newspaper and Newsletter | February 2024 | February 2023
Videos | February 2024 | February 2023
Bulk e-mail | October-2023
Other:
PREP-4. Outreach or educational activities are held at least 3 times a year. | December-2023 |  |  | GSD, NTRB
Identification of Lead | February 2023 | February 2023 |  |  | Civil Defence/Larnaca Municipality
Community tsunami safety workshops, town hall, or similar public / private meetings. | 2022-2024 | February 2023
Booth at community events and/or county fairs. | 2022-2024 | February 2023
Other: | 2022-2024 | February 2023
PREP-5. A community tsunami exercise is conducted at least every two years | November 2024 |  |  | Civil Defence
Identification of Lead | February 2023 | February 2023 |  |  | Civil Defence/Larnaca Municipality
Planning | 2023-2024
Conduct | November 2024
Evaluation | every 2 years |  |  |  | Civil Defence/Larnaca Municipality every two years
RESPONSE (RESP)
RESP-1. A community tsunami emergency operations plan is approved. | December 2023 | February 2023 |  | GSD/Civil Defence | Tender procedure
Identification of Lead | February 2023 | February 2023 |  | GSD/Civil Defence
Plan should include (requirements):
Tsunami hazard and risk assessment | December 2023 | December 2022 |  | GSD | Tender NOA INGV and IHC
Tsunami-hazard profile, including source locations, extend of inundation, run-up, previous or future tsunamis | July 2023 | December 2022 |  | GSD | Tender NOA INGV and IHC
Community vulnerability | December 2023 | December 2022
Detailed 24-hour warning point procedures | October 2023 |  |  | Civil Defence
Emergency operations center (EOC) activation criteria | October 2023 |  |  | Civil Defence
Tsunami criteria and procedures for the activation of the public warning system | October 2023 |  |  | Civil Defence
Contact information for all jurisdictional agencies and response partners | October 2023 |  |  | Civil Defence
Evacuation plans for tsunamis, roles of community entities/agencies, maps and protocols | October 2023 |  |  | Civil Defence
Procedures for updating information and determine when evacuated zones are safe | October 2023 |  |  | Civil Defence
Procedures for providing security for the evacuated zone(s) | October 2023 |  |  | Civil Defence
Procedures for reporting tsunami impacts in the community. | October 2023 |  |  | Civil Defence
Schools and critical facilities in the emergency operations plan | October 2023 |  |  | Civil Defence
Approval Tsunami Response Plan | December 2023 |  |  | Civil Defence/ NTRB
RESP-2. The capacity to manage emergency response operations during a tsunami is in place. | February 2024 | January2023
Identification of Lead | February 2023 | February 2023 |  | Civil Defence
Has a 24-hour operations or plan to activate an EOC for tsunami incidents
Has warning reception and dissemination capability
Has ability and authority to activate the public warning system in its area of responsability
Maintains the ability to communicate within and across jurisdictions
RESP-3. Redundant and reliable means (for community) to timely receive 24-hour official tsunami alerts are in place. | February 2024 | January2023
Identification of Lead | February 2023 | February 2023 |  | Civil Defence
Method 1
Method 2
Method 3
Other:
RESP-4. Redundant and reliable means (for community) to timely disseminate 24-hour official tsunami alerts to the public are in place. | February 2024 | January2023
Identification of Lead | February 2023 | February 2023 |  | Civil Defence
Method 1
Method 2
Method 3
Other: