## TR
UNESCO/IOC Tsunami Ready Recognition Programme
Name of Community
Update Date: 14 March 2023
Indicators & Actions | Target Completion (Date) | In Progress (Date) | Completed (Date) | Notes | Lead (agency, person)
NTRB | 2023-05-01 | Started and ongoing |  |  | Ignacio Aguirre Ayerbe - IHCantabria TWFP - National CPA NTWC NTRB Francisco Castro (Ayto. Chipiona) TRLC NTRB
TRLC |  |  | 2022-02-18 |  | Ignacio Aguirre Ayerbe (IHCantabria) Francisco Castro (Ayto. Chipiona)
National SOP workshops | march-2023 | Started and ongoing | apr-23 | Link
Local SOP workshops | april-2023 --> SEPT-2023 | Started and ongoing
ASSESSMENT (ASSESS)
ASSESS-1. Tsunami hazard zones are mapped and designated |  |  | ü
Maps and Products |  |  | 2022 |  | Ignacio Aguirre Ayerbe - IHCantabria Íñigo Aniel-Quiroga - IHCantabria
Report |  |  | 2022 | Summary of the method applied, in Sapnish
ASSESS-2. The number of people at risk in the tsunami hazard zone is estimated |  |  | ü
Identification of Lead |  |  | 2022 |  | Ignacio Aguirre Ayerbe (IHCantabria) Francisco Castro (Ayto. Chipiona)
Census data residents |  |  | 2022-11-01 | Also considering preople with special needs regarding mobiity. Spatial distribution of these person cannot be publicly display, but it is consider by Civi Protection volunteers and local police.
Census visitors | 2023-05-01 | Started and ongoing |  | No visitor census available. However, there is an estimate of the number of visitors during peak seasons. For spatial distribution of visitors, we are trying to get an estimate based on TRLC members knowledge, together with some statisctics.
Community validation of people at risk |  |  |  | Validation of this analysis is not planned. However, information will be collected from the community to estimate the spatial distribution of visitors.
ASSESS-3. Economic, infrastructural, political, and social resources are identified |  | Ongoing
Identification of Lead |  |  | 2022 |  | Ignacio Aguirre Ayerbe (IHCantabria) Francisco Castro (Ayto. Chipiona)
Initial list compiled |  |  | 2023-03-13 | Initial list compiled, in the process of being updated by the local focal point and TRLC.
List of resources | 2023-03-13 |  | apr-23
PREPAREDNESS (PREP)
PREP-1. Easily understood tsunami evacuation maps are approved. |  |  | ü
Identification of Lead |  |  | 2022 |  | Ignacio Aguirre Ayerbe (IHCantabria) Francisco Castro (Ayto. Chipiona)
Data layers: Infrastructures, roads, etc. |  |  | 2022 | Data used from spanish CNIG
Design and create Evacuation Map |  |  | 2022
Evacuation Map text (Backside) |  | Ongoing |  | Some information is available at national CPA, we are exploring how to adapt it and include it in the map.
Approval of Evacuation Map (official) |  |  | 2022
Printing of Tsunami Evacuation Map |  | Ongoing |  | Maps are not yet public. We have held its publication until the tsunami local ERP is approved.
Distribution of Tsunami Evacuation Map |  | Ongoing
PREP-2. Tsunami information including signage is publicly displayed. |  | Ongoing
Identification of Lead |  |  | 2022 |  | Ignacio Aguirre Ayerbe - IHCantabria Francisco Castro (Ayto. Chipiona) TRLC
Decide Type and artwork for Tsunami Signage / Public Displays | 2023-06-01 | Ongoing |  | To be harmonized in relation to the work carried out by the CPA and NTWC.
Signage / Public Displays Site Plan | 2023-06-01 | Ongoing | apr-23 | Locations agreed Spanish guidelines for tsunami signage recently approved by the NCPA (based on the UNE-EN ISO 7010:2020 standard)
Identification of Supplier and Quotes for Signage / Public Displays |  | Ongoing |  | Identifications of suppliers done Quotations requested
Procurement of Signage / Public Displays |  |  |  | Signage has been developed and installed by local initiative, but does not follow ISO standards. It will have to be removed to incorporate official signage
Installation of SIgnage / Public Displays
PREP-3. Outreach and public awareness and education resources are available and distributed. |  | Ongoing
Identification of Lead |  |  | 2022 |  | Ignacio Aguirre Ayerbe - IHCantabria Francisco Castro (Ayto. Chipiona) TRLC
Websites / Social Media |  |  | 2022/2023 | Social media
Brochures / Flyers | after approval of the tsunami ERP |  |  | Some work has been done on brochures including tsunami evacuation maps, which have not yet been distributed, pending approval of the tsunami ERP
Radio and Television |  |  | 2022/2023 | No specific videos have been produced to disseminate the TRRP or how to behave in the event of a tsunami. However, there are some videos for the media on the different events held, including the tsunami evacuation validation workshops, an evacuation exercise held one year ago. In addition, some members of the team have been interviewed for two different documentaries. All thsese activities have increased population awareness, based on TRLC preception (e.g., in carnival season it has been seen many inititaive related to tsunamis).
Newspaper and Newsletter |  |  | 2022/2023
Videos |  |  | 2022/2023
Bulk e-mail |  |  |  | Not planned
Other:
PREP-4. Outreach or educational activities are held at least 3 times a year. |  |  | ü
Identification of Lead |  |  | 2022 |  | Ignacio Aguirre Ayerbe - IHCantabria Francisco Castro (Ayto. Chipiona) TRLC
Community tsunami safety workshops, town hall, or similar public / private meetings. |  |  | 2022/2023 | List of workshops and meetings will be compiled
Booth at community events and/or county fairs. |  |  | 2022/2023
Other:
PREP-5. A community tsunami exercise is conducted at least every two years |  | Ongoing
Identification of Lead |  |  | 2022 |  | TWFP - National CPA NTWC NTRB TRLC NTRB Ignacio Aguirre Ayerbe - IHCantabria Francisco Castro (Ayto. Chipiona)
Planning | Ongoing |  |  | Official communication to TNC, NTWC, TWFP and DGEPC (Civil Protection at the Autonomous Community level) Municipal meeting planned for July 10th 2023
Conduct | 2023-11-01
Evaluation | 2023-11-01
RESPONSE (RESP)
RESP-1. A community tsunami emergency operations plan is approved. |  | Ongoing
Identification of Lead |  |  | 2022 |  | Director of PEM (Municipal Emergency Plan), Major Municipal Councilor for Civil Protection Local Police Chief Ignacio Aguirre Ayerbe - IHCantabria Francisco Castro (Ayto. Chipiona)
Plan should include (requirements):
Tsunami hazard and risk assessment |  |  | 2022 | Tsunami hazard + estimated exposure + population with special needs re-mobiity
Tsunami-hazard profile, including source locations, extend of inundation, run-up, previous or future tsunamis |  |  | 2022
Community vulnerability |  |  | 2022
Detailed 24-hour warning point procedures |  |  | 2022
Emergency operations center (EOC) activation criteria | 2023-10-01 | Ongoing
Tsunami criteria and procedures for the activation of the public warning system | 2023-10-01 | Ongoing
Contact information for all jurisdictional agencies and response partners | 2023-10-01 | Ongoing
Evacuation plans for tsunamis, roles of community entities/agencies, maps and protocols | 2023-10-01 | Ongoing
Procedures for updating information and determine when evacuated zones are safe | 2023-10-01 | Ongoing
Procedures for providing security for the evacuated zone(s) | 2023-10-01 | Ongoing
Procedures for reporting tsunami impacts in the community. | 2023-10-01 | Ongoing
Schools and critical facilities in the emergency operations plan |  |  | 2022
Approval Tsunami Response Plan | 2023-10-01 | Ongoing
RESP-2. The capacity to manage emergency response operations during a tsunami is in place. |  | Ongoing
Identification of Lead |  |  | 2022 |  | Director of PEM (Municipal Emergency Plan), Major Municipal Councilor for Civil Protection Local Police Chief Ignacio Aguirre Ayerbe - IHCantabria Francisco Castro (Ayto. Chipiona)
Has a 24-hour operations or plan to activate an EOC for tsunami incidents | 2023-10-01 | Ongoing
Has warning reception and dissemination capability | 2023-10-01 | Ongoing
Has ability and authority to activate the public warning system in its area of responsability | 2023-10-01 | Ongoing
Maintains the ability to communicate within and across jurisdictions | 2023-10-01 | Ongoing
RESP-3. Redundant and reliable means (for community) to timely receive 24-hour official tsunami alerts are in place. |  | Ongoing
Identification of Lead |  | Ongoing | 2022 |  | Director of PEM (Municipal Emergency Plan), Major Municipal Councilor for Civil Protection Local Police Chief Ignacio Aguirre Ayerbe - IHCantabria Francisco Castro (Ayto. Chipiona)
Method 1 | 2023-10-01 | Ongoing |  | Some methods already in place / need for a review
Method 2 | 2023-10-01 | Ongoing |  | Some methods already in place / need for a review
Method 3 | 2023-10-01 | Ongoing |  | Some methods already in place / need for a review
Other: | 2023-10-01 | Ongoing |  | Some methods already in place / need for a review
RESP-4. Redundant and reliable means (for community) to timely disseminate 24-hour official tsunami alerts to the public are in place. |  | Ongoing
Identification of Lead |  | Ongoing | 2022 |  | Director of PEM (Municipal Emergency Plan), Major Municipal Councilor for Civil Protection Local Police Chief Ignacio Aguirre Ayerbe - IHCantabria Francisco Castro (Ayto. Chipiona)
Method 1 | 2023-10-01 | Ongoing |  | Some methods already in place / need for a review
Method 2 | 2023-10-01 | Ongoing |  | Some methods already in place / need for a review
Method 3 | 2023-10-01 | Ongoing |  | Some methods already in place / need for a review
Other: | 2023-10-01 | Ongoing |  | Some methods already in place / need for a review
Progress march-may 23
Progress march-may 23
Completed march-may 23
Completed march-may 23
Completed march-may 23
Progress march-may 23
Progress march-may 23