CoastWAVE 2.0

First Project Steering Committee (PSC) Meeting

Meeting Report

Date: January 10, 2025
Time: 9:04 AM
Location: Online Zoom meeting

Attendees:

| CoastWAVE Phase 2-Project Steering Committee |  | Members |
| --- | --- | --- |
| Chair | : | Denis Chang Seng |
| ICG/NEAMTWS Chairperson or alternatively a nominated member by ICG/NEAMTWS officers | : | Alessandro Amato |
| One co-chairperson from each WGs and TTs (On a rotational basis or flexible arrangement options in case one is unable to participate) based on representative participation. | : | Didem Musavver Cambaz (WG2/3) Audrey GAILLER (WG1) Fabrizio Romano(TT-Non-seismic) Ceren Ozer Ozdinler (TT-TE) Eleni Daskalaki (TT-TR) Ignacio Aguirre Ayerbe (TT on Governance) |
| DG-ECHO representative | : | Olimpia Imperiali |
| CoastWAVE Project Staff | : | Derya Itir Vennin Anzhela Danilova |

UNDRR has not been represented in the first meeting

- Welcome and Opening Remarks

- Denis Chang Seng opened the meeting, emphasizing the importance of lessons learned from prior project phases to improve leadership, coordination, and administration.

  - Clarified PSC’s advisory role in providing strategic guidance, reviewing outputs, and overseeing progress.

  - Mentioned plans for biannual meetings with flexibility for urgent sessions.

2. Project Overall Summary and Status Report (Derya Vennin, project coordinator)

2.1 Review of PSC Composition, Roles and Responsibilities

- Members include representatives from UNESCO, EU, UNDRR, and various working groups and task teams of ICG/NEAMTWS.

- PSC’s role is advisory, ensuring compliance with project objectives and timelines.

- Secretariat responsibilities lie with UNESCO, with Denis chairing the committee.

- PSC’s primary role: Providing strategic guidance, reviewing outputs, and advising on adjustments.

- UNESCO’s role: Project management and reporting.

- Role of PSC is read from UNESCO-IOC DG ECHO CoastWAVE 2 project proposal

- Discussion highlighted:

  - Overlap between UNESCO’s coordination role and PSC’s advisory role.

  - Importance of maintaining distinct responsibilities to avoid conflicts.

2.2 Project Overview

- Vision: Empower coastal communities with sustainable resilience measures.

- Key Objectives:

  - Expand the network of tsunami-ready communities.

  - Enhance public awareness and preparedness.

  - Strengthen tsunami early warning systems.

  - Foster sustainable collaboration among stakeholders.

- Strategic focus areas include community-centric preparedness, technological integration, policy and governance, and regional collaboration.

- Timeline and Activities

- Upcoming Milestones:

  - Finalizing partnerships in remaining countries (Egypt, Morocco, Spain).

  - Regional Tsunami Ready training (January 14-15, 2025).

  - Expert meeting on tsunami sources (March 2025).

  - Project steering committee meeting (June 2025).

- Delays: Some delays due to summer breaks and extended partnership negotiations.

- Financial Overview

- First installment of $487,000 received and allocated 6% has been used so far.

- Budget distributed among nine partners based on deliverables and contributions.

- Challenges include higher partner budget requests compared to Phase 1.

- Special Topic: Expert Meeting on Tsunami Sources

- Dr. Gerassimos Papadopoulos outlined the plan for an expert meeting focusing on:

  - Hellenic Arc and Azores-Gibraltar fracture zones.

  - Multidisciplinary approaches involving seismologists, modelers, and other experts.

  - A report co-authored by experts as a deliverable.

  - Event tentatively scheduled for March 2025 (final dates pending logistics).

  - Online options will be discussed within PMU.

5. Key Contributions by Participants:

Olimpia Imperiali (ECHO Representative):

- Proposed showcasing Tsunami Ready certifications at the European Civil Protection Forum in 2026.

- Suggested aligning CoastWAVE with the Disaster Resilience Goals Initiative and the Union Preparedness Strategy.

- Emphasized leveraging the 20th anniversary of the 2004 Indian Ocean tsunami to renew awareness.

Denis Chang Seng (UNESCO Chair):

- Highlighted the sensitive and complex nature of ongoing partnership negotiations.

- Stressed the importance of including civil protection agencies to expand stakeholder engagement.

- Noted the successful recognition of CoastWAVE 2.0 as part of the Ocean Decade Tsunami Programme.

- Denis Chang Seng mentioned that online participation to the expert meeting may create interruptions to the progress of work.

- Supported the idea of organizing a webinar  or similar informational meeting for the expert meeting.

Derya Dilmen Vennin (Project Coordinator, UNESCO):

- Presented project vision and objectives: Expanding tsunami-ready communities, enhancing public awareness, and improving early warning systems.

- Shared updates on the project

- Discussed communication strategy development to align UNESCO and EU standards.

- Proposed alternative contracting mechanisms to address challenges in partnership agreements.

- Suggested involving Phase 1 communities in the NEAMWAVE exercise to increase engagement.

Alessandro Amato (ICG/NEAMTWS Chairperson):

- Raised concerns about roles within the PSC, advocating for clearer distinctions.

- Emphasized the importance of incorporating outputs from complementary projects like NEAM TsuMaps and NEAM Commitment.

- Suggested expanding the scope of expert meetings to include additional tsunami sources and regional risks.

Ignacio Aguirre Ayerbe (Co-chair of TT on Governance):

- Highlighted the need to align PSC proposals with existing project objectives and agreements.

- Proposed leveraging the 270th anniversary of the 1755 Lisbon tsunami in 2025 for awareness campaigns.

- Asked about the involvement/participation of the CoastWAVE 2 countries in the expert meeting on tsunami sources.

- Suggested that the expert meeting on tsunami sources have a hybrid component to allow other interested parties to attend as observers (closed microphones), given the importance of such a meeting and its relevance to key national stakeholders.

- Suggested UNESCO-IOC and Gerassimos Papadopoulus to organize an open webinar explaining the outcomes of the expert meeting to a wider audience.

Elena Daskalaki (Co-chair of TT on Tsunami Ready)

- Suggested that the expert meeting on tsunami sources have a hybrid component to allow other interested parties to attend as observers

Ceren Özer Sözdınler (Co-Chair of TT on Tsunami Exercise):

- Announced the rescheduling of the tsunami exercise to March 2026, aligning it with project timelines.

Dr. Gerassimos Papadopoulos (Expert Consultant):

- Outlined plans for the March 2025 expert meeting on tsunami sources, focusing on:

  - The Hellenic Arc and Azores-Gibraltar fracture zones.

  - Producing a co-authored technical report for ICG NEAMTWS.

- Highlighted the selection of 19 multidisciplinary experts to participate in the meeting.

6. Key Discussions:

- Challenges in PSC Membership and Roles

- Discussion on potential conflicts due to overlapping roles, especially for members with dual responsibilities.

- Alignment with Regional and Global Initiatives

- Agreed on the importance of showcasing project achievements at major platforms, including the European Civil Protection Forum and Disaster Resilience Goals Initiative.

- Planning the Expert Meeting on Tsunami Sources

- Focus areas: Hellenic Arc and Azores-Gibraltar fracture zones, with potential discussions on additional sources.

- Challenges in finalizing dates due to scheduling conflicts with major scientific events.

- Agreement on producing a technical report co-authored by participating experts.

7. Action Items:

- Finalize Partnerships: Resolve ongoing negotiations with Egypt, Morocco, and Türkiye.

- Coordinate Expert Meeting: Confirm dates, logistics, and participation for the March 2025 meeting.

- Prepare for Tsunami Exercise: Align March 2026 NEAMWave exercise and other activities with project objectives and ensure timely certification completion.

- Leverage Key Opportunities: Explore showcasing CoastWAVE achievements at the European Civil Protection Forum and commemorate the 1755 Lisbon tsunami anniversary.

8. Next Meeting:

- Date: June 2025 (Online)

Report Prepared By: Derya Vennin, project coordinator.
Date: January 13, 2025