## Table 1
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
Impact: Enhance the resilience and adaptive capacity of coastal communities in Kenya, Mozambique, Seychelles, and Madagascar by equipping policymakers, institutions, and researchers with reliable, accessible, and actionable sea-level data
PI 1. Percentage increase in the use of sea-level data for national policy, disaster risk reduction, and climate adaptation planning (disaggregated by institutional users and gender representation in decision-making processes).The level of resilience among coastal communities - not adressing the core of the project. Refrase it to: Number of new and old stations sharing across the region. |  | 0 | Global Ocean Report - IOC | National policy documents, disaster risk management frameworks, and climate adaptation strategies. - Data flow through the IOC and the | At least 20% of national policies reflect sea- level data considerati ons; capacity- building for policymak ers initiated. - Number of new and old stations sharing data. | 40% of national policies now include sea-level data; cross- sectoral coordinati on mechanis ms establishe d. - 10 stations in Madagascar, 2 stations Kenya, Seychelles 1, Mozambique 10. 10 New + 15 old. | At least 60% of national policies on disaster risk reduction and coastal manageme nt incorporat e real-time sea-level data within five years. | Annually | - Enhance availability and access of sea level data and promote its usage in informing national policies as well as reporting towards SDG and other global frameworks - Facilitate equitable empowerment of national experts, while ensuring both gender and age parity | Information generated will be used by member states to monitor for progress in monitoring sea level rise. In addition, UNESCO-IOC and the member states will use generated information for reporting against global and regional priorities including SDGs, Sendai Framework and the Paris Agreement and ocean science capacities through the Global Ocean Science Report (GOSR).
PI 2. Number of trained personnel (disaggregated by sex, age, and institutional affiliation) with enhanced capacity in sea-level data collection, interpretation, and application for decision-making. |  | N/a | IOCAFRICA survey 2022 | Pre- and post- training assessments, follow-up surveys, certification records. | 20 profession als trained, with at least 25% women and ECOPs; training materials and curriculum finalized. | 20 profession als trained, with at least 25% women and ECOPs; follow-up mentorshi p and peer learning sessions initiated. | At least 40 profession als, with at least 25% being women and youth, trained across all participati ng institutions by the end of the project. | Annualy
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
PI 3. Percentage increase in regional and international data-sharing and collaboration on sea-level monitoring, contributing to open- access databases and early warning systems. |  | 20 | IOCAFRICA and OIH project survey 2023 | Analysis of data- sharing agreements, assessment of participation in international networks, stakeholder consultations | Data- sharing agreement s signed with at least 50% of target institutions ; initial integration with regional platforms initiated. | 75% of participati ng institutions actively contributin g data to ODIS, OBIS, GLOSS and any regional platforms; operationa l protocols refined. | At least 75% of project- generated sea-level data is integrated into regional and global ocean observatio n platforms including ODIS, OBIS, GLOSS, ensuring open access and interopera bility
Outcome N° 1: Strengthened institutional capacity by enhancing the skills and knowledge of policymakers, institutions, and researchers. This will result in a more coordinated approach to sea-level data management and coastal resilience planning, enabling effective policy formulation and implementation.
PI 1. Number of institutions engaged in capacity development initiatives |  | 4 | IOCAFRICA Session reports | Annual Report | 6 | 8 | 14 | Annually | - Develop course material and subsequent training reports | Information generated will be used to report on capacities within partner marine
PI 2. Number of SEAMARCS institutions accessing data platforms |  | 0 | IOCAFRICA Survey (2021- 2022) | Annual reports | 4 | 16 | 20
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
PI 3. Number of collaborations on data and knowledge-sharing between regional and international partners to support sustainable coastal resilience initiatives |  | 2 | IODE reports | Annual reports | 4 | 6 | 10 |  | - Facilitate representative Stakeholder engagement and coordination - Participate in capacity building sessions and other project meetings | research institutions in the 4 beneficially countries. It will also be used to assess for technical capacity to monior sea level rise in the region
Output N°1: An “inexpensive sea level station in a box” concept with all the sensors, electronics, instructions and software is developed and deployed in four countries within the first trimester of the project.
PI 1. Number of sea level stations in a box developed, tested and successfully deployed |  | 0 | IOCAFRICA Survey (2021- 2022) | Quarterly reports | 4 | 6 | 10 | Quarterly | - Coordinate and oversee development and deployment of the sea level station in a box, ensuring they are functional and complying with international standards | - Long-term monitoring of sea level change -Enhanced partnerships between UNESCO-IOC and technology developers
PI 2. Number of countries provided with the new 'Sea-Level Station in a Box' |  | 0 |  | Annual report / counts | 4 | 4 | 4
Activity N°1: Procure the contractor to develop the 'Sea-Level Station in a Box'
PI 1. Number of calls for proposals developed and diffused across different UNESCO-IOC Communication channels |  | 0 | N/A | Call for proposals | 1 | 0 | 1 | Annually | Identify and liaise with contractor | Identification and selection of contractor
PI 2. Number of proposals received and reviewed |  | 0 | N/A | Count of proposals received | 3 | 3 | 6 | Annually
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
PI 3. Number of contracts signed to develop the ‘Sea-Level Station in a box’ |  | 0 | N/A | Number of contracts signed | 1 | 1 | 2 | Annually
Activity N° 2: Engage with suppliers and conduct procurement processes in line with international standards.
PI 1. Number of prototypes developed and piloted |  | 0 | N/A | Count the number of prototypes developed and tested | 3 |  | 3 | Monthly | Coordinate and oversee the development and deployment of the sea level station in a box, ensuring they are functional and complying with international standards | Acquisition of sea-level stations in line with international standards
PI 2. Number of ‘Sea-Level Stations in a box’ deployed across the four countries |  | 0 | N/A | Count of ‘Sea-Level Stations in a box’ successfully deployed | 4 | 6 | 10 | Quarterly
Activity N° 3: Quality assurance and monitoring- Conduct field testing and calibration of installed stations to ensure accuracy
PI 1. Number of field testing and calibration exercises conducted |  | 0 | N/A | Quartey reports | 2 | 2 | 4 | Quarterly | - UNESCO-IOC and national research and data institutions will assess the deployed sea- level stations and ensure they are well functional - The contractor and UNESCO-IOC will provide operational | Assess and confirm the functionality of the designed and procured sea level stations
PI 2. Number of operational manuals for long-term station maintenance and troubleshooting acquired. |  | 0 | N/A | Number of manuals received Annual reports | 1 | 2 | 3 | Annually
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
manuals for the national research institutions
Output N°2: Institutional capacities enhanced through specialized training programs and provision of necessary technical resources for policymakers, researchers, and technical staff.
PI 1. Number of institutions engaged in capacity development initiatives within the beneficiary countries |  | 3 | IOCAFRICA Session reports | Annual reports | 4 | 8 | 12 | Annually | - Coordinate the development and consolidation of training material - Organise and conduct workshops - Ensure inclusive selection and participation of trainees in the workshops - Assess the knowledge needs of different beneficiary countries and incorporate them in subsequent trainings | - Assess the knowledge/cap acity need gaps in the 4 countries - Facilitate planning of training event, while ensuring equal representation of relevant stakeholder groups
PI 2. Number of resources (e.g. manuals and policy documents) developed and diffused across the beneficiary countries |  | 0 | IOCAFRICA Session reports | Annual reports | 2 | 2 | 4 | Annually
PI 3. Number of national workshops and seminars organized with a focus on the interpretation and application of sea- level data. |  | 0 | National Reports IOCAFRICA Sessional reports | Training and Workshop reports | 4 | 4 | 8
Activity N° 1: Conduct training needs assessments to tailor capacity-building programs
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
PI 1. Number of ‘needs’ surveys developed and piloted among the beneficiary countries |  | 1 | IOCAFRICA Survey (2021- 2022) | Number of surveys developed and Piloted | 1 | 1 | 2 | Quarterly | - Assess the knowledge needs of different beneficiary countries | Assess and document the knowledge/cap acity gaps in the project beneficiary countries
PI 2. Number of responses to the surveys received |  | 0 | N/A | Count of survey responses | 4 | 6 | 10
Activity N° 2: Develop (online) training material with box installation instructions using the virtual and institutional ecosystem developed by OTGA
PI 1. Number of training modules and corresponding material developed and shared across the four beneficiary countries |  | 0 | National Reports IOCAFRICA Sessional reports | Count of successfully developed and piloted modules | 2 | 2 | 4 | Annualy | -Integrate the knowledge needs of different beneficiary countries in training plan - - Coordinate the development and consolidation of training - Organise training | - Information used to assess progress made towards developing capacity on using the new sea level station to monitor ocean parameters
PI 2. Number of workshops and trainings organized across the four beneficiary countries |  | 0 | IOCAFRICA Sessional reports | Training and Workshop reports | 4 | 4 | 8
PI 3. Number of participants, including women and early careers professionals, participating in the training and workshops |  | 0 | IOCAFRICA Sessional reports | Training and Workshop reports | 80 | 80 | 160
Activity N° 3: Quality assurance and monitoring: Undertake workshop and training review and feedback surveys across different beneficiary groups
PI 1. Number of feedback surveys developed |  | 0 | N/A | Count of feedback surveys developed and piloted | 1 | 2 | 3 | Quarterly | - Undertake follow-up survey and develop the report | Information will be used to evaluate the suitability of the training as well as its impact on the trainee needs
Add - qualitative indicator of precived usefullness from the training and workshop
PI 2. Number of responses to the feedback surveys received, including from women and early career professionals |  | 0 | N/A | Count of responses received | 25 | 50 | 75
Output N°3 A centralized, interoperable sea-level data management system is developed and deployed by the third trimester of the project
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
PI 1. Number of interoperable databases developed |  | 0 | OIH/IODE Report 2023 | Count of operational databases developed | 2 | 2 | 4 | Annually | - Develop interoperable databases -Add data to the newly developed database - Link existing national databases to newly developed platform - Provide training | Information will be used to; assess the data sharing/access needs within the beneficiary countries Inform the design of the data portal and interphase
PI 2. Number of data entries added and linked to the newly developed database |  | 0 | National reports - 2023 | Number of new databases | 4 | 6 | 10
PI 3. Number of personnel, including women and early career professionals, trained on the management and entry of data |  | 0 | National reports - 2023 | Training reports | 16 | 16 | 32
Activity N° 1: Conduct system requirements analysis and stakeholder consultations.
PI 1. Number of consultations with stakeholders |  | 1 | IOCAFRICA Survey (2021- 2022) | Number of surveys developed and Piloted | 1 | 1 | 2 | Monthly | - Organise stakeholder consultations and undertake stakeholder mapping | Information to be used to assess the data sharing/access needs within the beneficiary countries
PI 2. Number of existing data platforms mapped |  | 1 | IOCAFRICA - OIH Survey - (2022) | Number of existing data platforms identified | 1 | 1 | 2
Activity N° 2: Design and develop a user-friendly data management portal with real-time visualization capabilities, ensuring system interoperability with existing national and regional platforms.
PI 1. Number of operational “virtual sea level station maintenance interface” developed |  | 0 | N/A | Count of accessible interfaces developed | 0 | 1 | 1 | Quaterly | - Design and develop a user- friendly data management portal - Ensure national portals are linked to the | Information to be used in assessing data linkages and ease in accessing data within and between
PI 2. Number of national databases linked to the developed interoperable database |  | 0 | IOCAFRICA - OIH Survey - (2022) | Count of successfully linked National Databases | 0 | 4 | 4
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
[9 empty] | developed database | beneficiary states
Activity N° 3: Quality assurance and monitoring: Provide training to relevant stakeholders on data entry, management, and retrieval.
PI 1. Number of participants, including women and early careers professionals, participating in the trainings |  | 0 | N/A | Report of the training events | 8 | 8 | 16 | Biannually | - Coordinate the development and consolidation of training - Organise training | Information will be used to document the new knowledge impacted on trainees with respect to data entry, management and retrieval
PI 2. Number of stakeholder groups participating in the training |  | 0 | N/A | Count of stakeholder groups | 1 | 5 | 6
Output N°4: Targeted training programs and capacity-building workshops delivered by the second trimester of the project
PI 1. Number of training sessions undertaken within the four beneficiary countries |  | 2 | IOCAFRICA Session reports | Reports of successful training events | 1 | 1 | 2 | Biannually | Coordinate the development and consolidation of training material - Organise and conduct workshops - Ensure inclusive selection and participation of trainees in the workshops - Assess the knowledge needs of different beneficiary countries and | Information will be used to assess the number of personnel (including women and early career professionals) impacted with new skills. In addition, it will be used to follow-up on number of peer-to-peer groups formed and assess their impact on the learning process
PI 2. Number of training / educational materials developed |  | 1 | IOCAFRICA Session reports | Count of training materials developed and used in training events | 1 | 1 | 2
PI 3. Number of participants, including women and early careers professionals, participating in the trainings |  | 4 | IOCAFRICA Session reports | Reports of the training sessions | 10 | 10 | 20
PI 4. Number of peer-to-peer learning opportunities initiated |  | 0 | IOCAFRICA Session reports | Surveys among the stakeholder groups | 2 | 2 | 4
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
incorporate them in subsequent trainings
Activity N° 1: Identify key stakeholders and customise training content to their specific needs
PI 1. Number of stakeholder groups identified |  | 1 | Project concept note | Stakeholder mapping report | 2 | 4 | 6 | Quarterly | - Identify and map out potential beneficiaries of the training - Develop and consolidate training material | The information will be used to customise the training material, with respect to the different learning groups documented
PI 2. Number of types of customised training material developed |  | 1 | OTGA and OIH reports | Count of training materials developed | 1 | 2 | 3
Activity N° 2: . Organize in-person and virtual training sessions on sea-level monitoring and data interpretation
PI 1. Number of training sessions organized |  | 0 | IOCAFRICA reports | Count of number of training reports | 0 | 1 | 1 | Annually | - Coordinate the development and consolidation of training material - Organise training | Information will be used to assess the number of personnel (including women and early career professionals) impacted with new skills
PI 2. Number of participants, including women and early career professionals participating in the training |  | 0 | IOCAFRICA reports | List of participants in training events | 0 | 30 | 30
Activity N° 3: Facilitate knowledge exchange through peer-to-peer learning opportunities.
PI 1. Number of peer-to-peer groups formed |  | 0 | IOCAFRICA reports | Count of recorded peer-to-peer working groups formed | 1 | 2 | 3 | Annually | - Coordinate formation, meeting and reporting of peer-to-peer groups | Information will be used to follow-up on number of peer-to-peer groups formed
PI 2. Number of peer-to-peer sessions |  | 0 | IOCAFRICA reports | Records of peer–to– peer sessions | 2 | 6 | 8
Quantitative and qualitative performance indicator (PI) (disaggregated by: sex, age) |  | Baseline | Source | Means of verification (Method) | Milestone Year 1 | Milestone Year 2 | Target | Frequency | Stakeholders responsibility | Information use/Audience
PI 3. Number of trainees, including women and early-career professionals participating in the peer-to-peer sessions |  | 0 | IOCAFRICA reports | List of trainees in peer-to-peer groups | 6 | 14 | 20 |  |  | and assess their impact on the learning process
Activity N° 4: Develop educational materials and training manuals for long-term reference
PI 1. Number of educational material and manuals developed and deployed for the training |  | 1 | OTGA and OIH repositorie s | Count of number of training material developed and shared with trainees | 1 | 1 | 2 | Annually | - Coordinate the development and consolidation of training materials and manuals - Oversee the distribution of training material | The information will be used to assess long- term change in the knowledge development and sharing among the trainees within the beneficiary countries
PI 2. Number of experts, including women, engaged in the development of the training material |  | 0 | IOCAFRICA reports | List of trainees as per training reports | 0 | 4 | 4
Activity N° 5: Quality assurance and monitoring: Implement follow-up training to reinforce capacity-building efforts.
PI 1. Number of trainees involved in the follow-up training |  | 0 | N/A | List of trainees as per training reports | 0 | 20 | 20 | Annualy | - Coordinate the development and consolidation of training material - Organise training | The information will be used to assess long- term change in the knowledge development and sharing among the trainees within the beneficiary countries
PI 2. Number of reports developed on follow-up trainings |  | 0 | N/A | Count of training reports | 0 | 1 | 1
PI3. Number of follow-up trainings conducted |  | 0 | N/A | Count of training reports | 0 | 1 | 1